## Annex-IV
Annexure-IV
Year wise Financial and Physical Target Plan
Name of the Project : Coastal Towns Climate Resilience Project.
Name of Agency/Division/Ministry: LGED/LGD/LGRD&C | [26 empty] | (Taka In Lac)
Economic Code | Economic Sub-Code | Sub-Code Description (in detail) | Total Physical & Financial Target |  |  |  |  | Year-1 |  |  | Year-2 |  |  | Year-3 |  |  | Year-4 |  |  | Year-5 |  |  | Year-6 |  |  | Year-7
[8 empty] | FY 2022-23 |  |  | FY 2023-24 |  |  | FY 2024-25 |  |  | FY 2025-26 |  |  | FY 2026-27 |  |  | FY 2027-28 |  |  | FY 2028-29
|  |  | Unit | Unit Cost | Quantity | Total Cost | Weight | Financial Amount | Physical |  | Financial Amount | Physical |  | Financial Amount | Physical |  | Financial Amount | Physical |  | Financial Amount | Physical |  | Financial Amount | Physical |  | Financial Amount | Physical
[9 empty] | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project |  | % of Item | % of Project
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
(A) Revenue Component
Pay of Officer:
3111 | 3111101 | Basic Pay (Officer) | PM | 0.64 | 1932 | 1236.48 | 0.004638 | 24.7296 | 2 | 0.0092759 | 123.648 | 10 | 0.04638 | 309.12 | 25 | 0.11595 | 309.12 | 25 | 0.11595 | 309.12 | 25 | 0.11595 | 123.648 | 10 | 0.04638 | 37.0944 | 3 | 0.013914
|  | Sub Total |  |  |  | 1236.48 |  | 24.7296 |  |  | 123.648 |  |  | 309.12 |  |  | 309.12 |  |  | 309.12 |  |  | 123.648 |  |  | 37.0944
Pay of Empolyee:
3111 | 3111201 | Basic Pay (Employee) | PM | 0.40478 | 504 | 204.01 | 0.00076523 | 4.0802 | 2 | 0.0015305 | 20.401 | 10 | 0.0076523 | 51.0025 | 25 | 0.019131 | 51.0025 | 25 | 0.019131 | 51.0025 | 25 | 0.019131 | 20.401 | 10 | 0.0076523 | 6.1203 | 3 | 0.0022957
|  | Sub Total |  |  |  | 204.01 |  | 4.0802 |  |  | 20.401 |  |  | 51.0025 |  |  | 51.0025 |  |  | 51.0025 |  |  | 20.401 |  |  | 6.1203
Allowances:
3111 | 3111301 | Charge Allowance | PM | 0.057 | 420 | 23.94 | 8.9797e-05 | 0.4788 | 2 | 0.00017959 | 2.394 | 10 | 0.00089797 | 5.985 | 25 | 0.0022449 | 5.985 | 25 | 0.0022449 | 5.985 | 25 | 0.0022449 | 2.394 | 10 | 0.00089797 | 0.7182 | 3 | 0.00026939
3111 | 3111302 | Conveyance Allowance | PM | 0.0030159 | 504 | 1.52 | 5.7014e-06 | 0.0304 | 2 | 1.1403e-05 | 0.152 | 10 | 5.7014e-05 | 0.38 | 25 | 0.00014254 | 0.38 | 25 | 0.00014254 | 0.38 | 25 | 0.00014254 | 0.152 | 10 | 5.7014e-05 | 0.0456 | 3 | 1.7104e-05
3111 | 3111306 | Educational Allowance | PM | 0.0082759 | 2436 | 20.16 | 7.5619e-05 | 0.4032 | 2 | 0.00015124 | 2.016 | 10 | 0.00075619 | 5.04 | 25 | 0.0018905 | 5.04 | 25 | 0.0018905 | 5.04 | 25 | 0.0018905 | 2.016 | 10 | 0.00075619 | 0.6048 | 3 | 0.00022686
3111 | 3111310 | Housing Rent Allowances | PM | 0.35071 | 2436 | 854.34 | 0.0032046 | 17.0868 | 2 | 0.0064092 | 85.434 | 10 | 0.032046 | 213.585 | 25 | 0.080114 | 213.585 | 25 | 0.080114 | 213.585 | 25 | 0.080114 | 85.434 | 10 | 0.032046 | 25.6302 | 3 | 0.0096137
3111 | 3111311 | Medical Allowance | PM | 0.015 | 2436 | 36.54 | 0.00013706 | 0.7308 | 2 | 0.00027412 | 3.654 | 10 | 0.0013706 | 9.135 | 25 | 0.0034265 | 9.135 | 25 | 0.0034265 | 9.135 | 25 | 0.0034265 | 3.654 | 10 | 0.0013706 | 1.0962 | 3 | 0.00041118
3111 | 3111312 | Mobile/Cell Phone Allowance | PM | 0.016 | 420 | 6.72 | 2.5206e-05 | 0.1344 | 2 | 5.0413e-05 | 0.672 | 10 | 0.00025206 | 1.68 | 25 | 0.00063016 | 1.68 | 25 | 0.00063016 | 1.68 | 25 | 0.00063016 | 0.672 | 10 | 0.00025206 | 0.2016 | 3 | 7.5619e-05
3111 | 3111314 | Tiffin Allowance | PM | 0.0030159 | 504 | 1.52 | 5.7014e-06 | 0.0304 | 2 | 1.1403e-05 | 0.152 | 10 | 5.7014e-05 | 0.38 | 25 | 0.00014254 | 0.38 | 25 | 0.00014254 | 0.38 | 25 | 0.00014254 | 0.152 | 10 | 5.7014e-05 | 0.0456 | 3 | 1.7104e-05
3111 | 3111325 | Festival Allowance | Nos. | 0.65195 | 435 | 283.6 | 0.0010638 | 5.672 | 2 | 0.0021275 | 28.36 | 10 | 0.010638 | 70.9 | 25 | 0.026594 | 70.9 | 25 | 0.026594 | 70.9 | 25 | 0.026594 | 28.36 | 10 | 0.010638 | 8.508 | 3 | 0.0031913
3111 | 3111328 | Rest & Recreation Allowance | Nos. | 0.6 | 87 | 52.2 | 0.0001958 | 1.044 | 2 | 0.0003916 | 5.22 | 10 | 0.001958 | 13.05 | 25 | 0.004895 | 13.05 | 25 | 0.004895 | 13.05 | 25 | 0.004895 | 5.22 | 10 | 0.001958 | 1.566 | 3 | 0.0005874
3111 | 3111335 | Bangla New Year Allowance | Nos. | 0.15 | 232 | 34.8 | 0.00013053 | 0.696 | 2 | 0.00026107 | 3.48 | 10 | 0.0013053 | 8.7 | 25 | 0.0032633 | 8.7 | 25 | 0.0032633 | 8.7 | 25 | 0.0032633 | 3.48 | 10 | 0.0013053 | 1.044 | 3 | 0.0003916
3111 | 3111338 | Other Allowance | L.S | 1.1903 | 232 | 276.16 | 0.0010359 | 5.5232 | 2 | 0.0020717 | 27.616 | 10 | 0.010359 | 69.04 | 25 | 0.025896 | 69.04 | 25 | 0.025896 | 69.04 | 25 | 0.025896 | 27.616 | 10 | 0.010359 | 8.2848 | 3 | 0.0031076
|  | Sub Total |  |  |  | 1591.5 |  | 31.83 |  |  | 159.15 |  |  | 397.875 |  |  | 397.875 |  |  | 397.875 |  |  | 159.15 |  |  | 47.745
Supplies and Services:
3211 | 3211111 | Seminar & Conference Expenses | Nos. | 7.6667 | 30 | 230 | 0.00086272 | 4.6 | 2 | 0.0017254 | 23 | 10 | 0.0086272 | 57.5 | 25 | 0.021568 | 57.5 | 25 | 0.021568 | 57.5 | 25 | 0.021568 | 23 | 10 | 0.0086272 | 6.9 | 3 | 0.0025881
3211 | 3211113 | Electricity | Month | 2.8571 | 84 | 240 | 0.00090023 | 4.8 | 2 | 0.0018005 | 24 | 10 | 0.0090023 | 60 | 25 | 0.022506 | 60 | 25 | 0.022506 | 60 | 25 | 0.022506 | 24 | 10 | 0.0090023 | 7.2 | 3 | 0.0027007
3211 | 3211119 | Postage | Month | 0.11905 | 84 | 10 | 3.7509e-05 | 0.2 | 2 | 7.5019e-05 | 1 | 10 | 0.00037509 | 2.5 | 25 | 0.00093773 | 2.5 | 25 | 0.00093773 | 2.5 | 25 | 0.00093773 | 1 | 10 | 0.00037509 | 0.3 | 3 | 0.00011253
3211 | 3211120 | Telephone | Month | 0.77381 | 84 | 65 | 0.00024381 | 1.3 | 2 | 0.00048762 | 6.5 | 10 | 0.0024381 | 16.25 | 25 | 0.0060953 | 16.25 | 25 | 0.0060953 | 16.25 | 25 | 0.0060953 | 6.5 | 10 | 0.0024381 | 1.95 | 3 | 0.00073143
3211 | 3211125 | Advertising Expenses | Nos. | 0.42035 | 678 | 285 | 0.001069 | 5.7 | 2 | 0.002138 | 28.5 | 10 | 0.01069 | 71.25 | 25 | 0.026725 | 71.25 | 25 | 0.026725 | 71.25 | 25 | 0.026725 | 28.5 | 10 | 0.01069 | 8.55 | 3 | 0.0032071
3211 | 3211126 | Audio -VDO/Film Production | Nos. | 2.1739 | 23 | 50 | 0.00018755 | 1 | 2 | 0.00037509 | 5 | 10 | 0.0018755 | 12.5 | 25 | 0.0046887 | 12.5 | 25 | 0.0046887 | 12.5 | 25 | 0.0046887 | 5 | 10 | 0.0018755 | 1.5 | 3 | 0.00056264
3211 | 3211128 | Publications | L.S | 0 | 0 | 85 | 0.00031883 | 1.7 | 2 | 0.00063766 | 8.5 | 10 | 0.0031883 | 21.25 | 25 | 0.0079707 | 21.25 | 25 | 0.0079707 | 21.25 | 25 | 0.0079707 | 8.5 | 10 | 0.0031883 | 2.55 | 3 | 0.00095649
3211 | 3211131 | Out sourcing | PM | 0.35714 | 8820 | 3150 | 0.011815 | 63 | 2 | 0.023631 | 315 | 10 | 0.11815 | 787.5 | 25 | 0.29539 | 787.5 | 25 | 0.29539 | 787.5 | 25 | 0.29539 | 315 | 10 | 0.11815 | 94.5 | 3 | 0.035446
3221 | 3221104 | Registration Fee | L.S | 0 | 0 | 324.9 | 0.0012187 | 6.498 | 2 | 0.0024374 | 32.49 | 10 | 0.012187 | 81.225 | 25 | 0.030467 | 81.225 | 25 | 0.030467 | 81.225 | 25 | 0.030467 | 32.49 | 10 | 0.012187 | 9.747 | 3 | 0.003656
3231 | 3231201 | DomesticTraining | Nos. | 7.5 | 50 | 375 | 0.0014066 | 7.5 | 2 | 0.0028132 | 37.5 | 10 | 0.014066 | 93.75 | 25 | 0.035165 | 93.75 | 25 | 0.035165 | 93.75 | 25 | 0.035165 | 37.5 | 10 | 0.014066 | 11.25 | 3 | 0.0042198
3231 | 3231201 | ForeignTraining | Nos. | 116.6667 | 3 | 350 | 0.0013128 | 7 | 2 | 0.0026257 | 35 | 10 | 0.013128 | 87.5 | 25 | 0.032821 | 87.5 | 25 | 0.032821 | 87.5 | 25 | 0.032821 | 35 | 10 | 0.013128 | 10.5 | 3 | 0.0039385
3241 | 3241101 | Domestic Travel Expenses | L.S | 0 | 0 | 364.75 | 0.0013682 | 7.295 | 2 | 0.0027363 | 36.475 | 10 | 0.013682 | 91.1875 | 25 | 0.034204 | 91.1875 | 25 | 0.034204 | 91.1875 | 25 | 0.034204 | 36.475 | 10 | 0.013682 | 10.9425 | 3 | 0.0041045
3241 | 3241102 | Domestic Trasfer Expenses | L.S | 0 | 0 | 50 | 0.00018755 | 1 | 2 | 0.00037509 | 5 | 10 | 0.0018755 | 12.5 | 25 | 0.0046887 | 12.5 | 25 | 0.0046887 | 12.5 | 25 | 0.0046887 | 5 | 10 | 0.0018755 | 1.5 | 3 | 0.00056264
3243 | 3243101 | Petrol, Oil and Lubricants | L.S | 0 | 0 | 850 | 0.0031883 | 17 | 2 | 0.0063766 | 85 | 10 | 0.031883 | 212.5 | 25 | 0.079707 | 212.5 | 25 | 0.079707 | 212.5 | 25 | 0.079707 | 85 | 10 | 0.031883 | 25.5 | 3 | 0.0095649
3243 | 3243102 | Gas and Fuel | L.S | 0 | 0 | 540 | 0.0020255 | 10.8 | 2 | 0.004051 | 54 | 10 | 0.020255 | 135 | 25 | 0.050638 | 135 | 25 | 0.050638 | 135 | 25 | 0.050638 | 54 | 10 | 0.020255 | 16.2 | 3 | 0.0060765
3255 | 3255101 | Computer Consumables | L.S | 0 | 0 | 250 | 0.00093773 | 5 | 2 | 0.0018755 | 25 | 10 | 0.0093773 | 62.5 | 25 | 0.023443 | 62.5 | 25 | 0.023443 | 62.5 | 25 | 0.023443 | 25 | 10 | 0.0093773 | 7.5 | 3 | 0.0028132
3255 | 3255104 | Stamps & Seals | L.S | 0 | 0 | 21 | 7.877e-05 | 0.42 | 2 | 0.00015754 | 2.1 | 10 | 0.0007877 | 5.25 | 25 | 0.0019692 | 5.25 | 25 | 0.0019692 | 5.25 | 25 | 0.0019692 | 2.1 | 10 | 0.0007877 | 0.63 | 3 | 0.00023631
3255 | 3255105 | Others Stationery | L.S | 0 | 0 | 208 | 0.0007802 | 4.16 | 2 | 0.0015604 | 20.8 | 10 | 0.007802 | 52 | 25 | 0.019505 | 52 | 25 | 0.019505 | 52 | 25 | 0.019505 | 20.8 | 10 | 0.007802 | 6.24 | 3 | 0.0023406
3257 | 3257101 | Consultancy | PM | 3.156 | 4544 | 14341 | 0.053792 | 286.82 | 2 | 0.10758 | 1434.1 | 10 | 0.53792 | 3585.25 | 25 | 1.3448 | 3585.25 | 25 | 1.3448 | 3585.25 | 25 | 1.3448 | 1434.1 | 10 | 0.53792 | 430.23 | 3 | 0.16138
3257 | 3257104 | Survey | Nos. | 7.7809 | 110 | 855.9 | 0.0032104 | 17.118 | 2 | 0.0064209 | 85.59 | 10 | 0.032104 | 213.975 | 25 | 0.080261 | 213.975 | 25 | 0.080261 | 213.975 | 25 | 0.080261 | 85.59 | 10 | 0.032104 | 25.677 | 3 | 0.0096313
3257 | 3257206 | Honorarium / Remuneration | Nos. | 0.33333 | 510 | 170 | 0.00063766 | 3.4 | 2 | 0.0012753 | 17 | 10 | 0.0063766 | 42.5 | 25 | 0.015941 | 42.5 | 25 | 0.015941 | 42.5 | 25 | 0.015941 | 17 | 10 | 0.0063766 | 5.1 | 3 | 0.001913
|  | Sub Total |  |  |  | 22815.55 |  | 456.311 |  |  | 2281.555 |  |  | 5703.8875 |  |  | 5703.8875 |  |  | 5703.8875 |  |  | 2281.555 |  |  | 684.4665
Repair, Maintenance and Rehabilitation
3258 | 3258101 | Motor Vehicle | L.S | 0 | 0 | 1062 | 0.0039835 | 21.24 | 2 | 0.007967 | 106.2 | 10 | 0.039835 | 265.5 | 25 | 0.099587 | 265.5 | 25 | 0.099587 | 265.5 | 25 | 0.099587 | 106.2 | 10 | 0.039835 | 31.86 | 3 | 0.01195
3258 | 3258102 | Furniture | L.S | 0 | 0 | 138 | 0.00051763 | 2.76 | 2 | 0.0010353 | 13.8 | 10 | 0.0051763 | 34.5 | 25 | 0.012941 | 34.5 | 25 | 0.012941 | 34.5 | 25 | 0.012941 | 13.8 | 10 | 0.0051763 | 4.14 | 3 | 0.0015529
3258 | 3258103 | Computer | L.S | 0 | 0 | 110 | 0.0004126 | 2.2 | 2 | 0.00082521 | 11 | 10 | 0.004126 | 27.5 | 25 | 0.010315 | 27.5 | 25 | 0.010315 | 27.5 | 25 | 0.010315 | 11 | 10 | 0.004126 | 3.3 | 3 | 0.0012378
3258 | 3258105 | Machinaris and Equipment | L.S | 0 | 0 | 110 | 0.0004126 | 2.2 | 2 | 0.00082521 | 11 | 10 | 0.004126 | 27.5 | 25 | 0.010315 | 27.5 | 25 | 0.010315 | 27.5 | 25 | 0.010315 | 11 | 10 | 0.004126 | 3.3 | 3 | 0.0012378
|  | Sub Total |  |  |  | 1420 |  | 28.4 |  |  | 142 |  |  | 355 |  |  | 355 |  |  | 355 |  |  | 142 |  |  | 42.6
|  | Total Revenue Component: A |  |  |  | 27267.54 |  | 545.3508 |  |  | 2726.754 |  |  | 6816.885 |  |  | 6816.885 |  |  | 6816.885 |  |  | 2726.754 |  |  | 818.0262
(B) Capital Component
Acquisition of Assets
4112 | 4112101 | Jeep | Nos | 100 | 7 | 700 | 0.0026257 | 14 | 2 | 0.0052513 | 70 | 10 | 0.026257 | 175 | 25 | 0.065641 | 175 | 25 | 0.065641 | 175 | 25 | 0.065641 | 70 | 10 | 0.026257 | 21 | 3 | 0.007877
4112 | 4112101 | Double Cabin Pickup/ Carryboy | Nos | 76.661 | 29 | 2223.17 | 0.008339 | 44.4634 | 2 | 0.016678 | 222.317 | 10 | 0.08339 | 555.7925 | 25 | 0.20847 | 555.7925 | 25 | 0.20847 | 555.7925 | 25 | 0.20847 | 222.317 | 10 | 0.08339 | 66.6951 | 3 | 0.025017
4112 | 4112101 | Micro Bus | Nos | 76.515 | 2 | 153.03 | 0.00057401 | 3.0606 | 2 | 0.001148 | 15.303 | 10 | 0.0057401 | 38.2575 | 25 | 0.01435 | 38.2575 | 25 | 0.01435 | 38.2575 | 25 | 0.01435 | 15.303 | 10 | 0.0057401 | 4.5909 | 3 | 0.001722
4112 | 4112101 | Motor Cycle | Nos | 2.5521 | 24 | 61.25 | 0.00022974 | 1.225 | 2 | 0.00045949 | 6.125 | 10 | 0.0022974 | 15.3125 | 25 | 0.0057436 | 15.3125 | 25 | 0.0057436 | 15.3125 | 25 | 0.0057436 | 6.125 | 10 | 0.0022974 | 1.8375 | 3 | 0.00068923
4112 | 4112202 | Computers and Accessories [Appendix-4(d)] | Nos | 1.994 | 163 | 325.03 | 0.0012192 | 6.5006 | 2 | 0.0024383 | 32.503 | 10 | 0.012192 | 81.2575 | 25 | 0.030479 | 81.2575 | 25 | 0.030479 | 81.2575 | 25 | 0.030479 | 32.503 | 10 | 0.012192 | 9.7509 | 3 | 0.0036575
4112 | 4112304 | Engineering and other Equipments [Appendix-4(b) and 4(c)] | Nos/Set | 8.5387 | 660 | 5635.52 | 0.021138 | 112.7104 | 2 | 0.042277 | 563.552 | 10 | 0.21138 | 1408.88 | 25 | 0.52846 | 1408.88 | 25 | 0.52846 | 1408.88 | 25 | 0.52846 | 563.552 | 10 | 0.21138 | 169.0656 | 3 | 0.063415
4112 | 4112314 | Furniture [Appendix-4(d)] | L.S | 0 | 0 | 152 | 0.00057014 | 3.04 | 2 | 0.0011403 | 15.2 | 10 | 0.0057014 | 38 | 25 | 0.014254 | 38 | 25 | 0.014254 | 38 | 25 | 0.014254 | 15.2 | 10 | 0.0057014 | 4.56 | 3 | 0.0017104
|  | Sub Total |  |  |  | 9250 |  | 185 |  |  | 925 |  |  | 2312.5 |  |  | 2312.5 |  |  | 2312.5 |  |  | 925 |  |  | 277.5
4141 | 4141101 | Land Acquisition & Resettlement (Compensation for Land, structure & other assets including re-location, transitional training, vulnerable, documentation, monitoring, mitigation capacity measures & all other cost related to address ADB Safeguard issues) | Acre | 158.401 | 66.54 | 10540 | 0.039535 | 210.8 | 2 | 0.07907 | 1054 | 10 | 0.39535 | 2635 | 25 | 0.98837 | 2635 | 25 | 0.98837 | 2635 | 25 | 0.98837 | 1054 | 10 | 0.39535 | 316.2 | 3 | 0.1186
|  | Sub Total |  |  |  | 10540 |  | 210.8 |  |  | 1054 |  |  | 2635 |  |  | 2635 |  |  | 2635 |  |  | 1054 |  |  | 316.2
Construction of Works
Stage-I
4111 | 4111304 | Roads | Km | 238.9632 | 298.387 | 71303.5 | 0.26745 | 1426.07 | 2 | 0.53491 | 7130.35 | 10 | 2.6745 | 17825.875 | 25 | 6.6864 | 17825.875 | 25 | 6.6864 | 17825.875 | 25 | 6.6864 | 7130.35 | 10 | 2.6745 | 2139.105 | 3 | 0.80236
4111 | 4111303 | Bridges | m | 13.9576 | 920 | 12841.01 | 0.048166 | 256.8202 | 2 | 0.096332 | 1284.101 | 10 | 0.48166 | 3210.2525 | 25 | 1.2041 | 3210.2525 | 25 | 1.2041 | 3210.2525 | 25 | 1.2041 | 1284.101 | 10 | 0.48166 | 385.2303 | 3 | 0.1445
4111 | 4111307 | Drainage and flood control | Km | 334.3158 | 140.97 | 47128.5 | 0.17678 | 942.57 | 2 | 0.35355 | 4712.85 | 10 | 1.7678 | 11782.125 | 25 | 4.4194 | 11782.125 | 25 | 4.4194 | 11782.125 | 25 | 4.4194 | 4712.85 | 10 | 1.7678 | 1413.855 | 3 | 0.53033
Others Structures
4111 | 4111317 | (a) Cyclone shelters | Nos. | 464.9435 | 23 | 10693.7 | 0.040111 | 213.874 | 2 | 0.080223 | 1069.37 | 10 | 0.40111 | 2673.425 | 25 | 1.0028 | 2673.425 | 25 | 1.0028 | 2673.425 | 25 | 1.0028 | 1069.37 | 10 | 0.40111 | 320.811 | 3 | 0.12033
4111 | 4111317 | (b) Solid Waste Management | Nos. | 2125 | 4 | 8500 | 0.031883 | 170 | 2 | 0.063766 | 850 | 10 | 0.31883 | 2125 | 25 | 0.79707 | 2125 | 25 | 0.79707 | 2125 | 25 | 0.79707 | 850 | 10 | 0.31883 | 255 | 3 | 0.095649
4111 | 4111317 | (c) Green Space | Nos. | 750 | 2 | 1500 | 0.0056264 | 30 | 2 | 0.011253 | 150 | 10 | 0.056264 | 375 | 25 | 0.14066 | 375 | 25 | 0.14066 | 375 | 25 | 0.14066 | 150 | 10 | 0.056264 | 45 | 3 | 0.016879
4111 | 4111317 | (d) Nature-Base Solution | Nos. | 760 | 3 | 2280 | 0.0085521 | 45.6 | 2 | 0.017104 | 228 | 10 | 0.085521 | 570 | 25 | 0.2138 | 570 | 25 | 0.2138 | 570 | 25 | 0.2138 | 228 | 10 | 0.085521 | 68.4 | 3 | 0.025656
4111 | 4111317 | (e) Slum Improvement | Nos. | 79.5455 | 22 | 1750 | 0.0065641 | 35 | 2 | 0.013128 | 175 | 10 | 0.065641 | 437.5 | 25 | 0.1641 | 437.5 | 25 | 0.1641 | 437.5 | 25 | 0.1641 | 175 | 10 | 0.065641 | 52.5 | 3 | 0.019692
Stage-II
Others Structures
4111 | 4111317 | (a) Multipurpose Market | Nos. | 564.8571 | 21 | 11862 | 0.044494 | 237.24 | 2 |  | 1186.2 | 10 | 0.44494 | 2965.5 | 25 | 1.1123 | 2965.5 | 25 | 1.1123 | 2965.5 | 25 | 1.1123 | 1186.2 | 10 | 0.44494 | 355.86 | 3 | 0.13348
4111 | 4111317 | (b) Bus Terminal | Nos. | 2125 | 4 | 8500 | 0.031883 | 170 | 2 |  | 850 | 10 | 0.31883 | 2125 | 25 | 0.79707 | 2125 | 25 | 0.79707 | 2125 | 25 | 0.79707 | 850 | 10 | 0.31883 | 255 | 3 | 0.095649
4111 | 4111317 | (c) Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/ Bus Bay/Poltun etc. | Nos. | 458.2405 | 22 | 10081.29 | 0.037814 | 201.6258 | 2 | 0.075629 | 1008.129 | 10 | 0.37814 | 2520.3225 | 25 | 0.94536 | 2520.3225 | 25 | 0.94536 | 2520.3225 | 25 | 0.94536 | 1008.129 | 10 | 0.37814 | 302.4387 | 3 | 0.11344
|  | Sub Total |  |  |  | 186440 |  | 3728.8 |  |  | 18644 |  |  | 46610 |  |  | 46610 |  |  | 46610 |  |  | 18644 |  |  | 5593.2
Block Allocation
7215 | 7215205 | Block Allocation (Commitment Charge) |  |  |  | 284 | 0.0010653 | 5.68 | 2 | 0.0021305 | 28.4 | 10 | 0.010653 | 71 | 25 | 0.026632 | 71 | 25 | 0.026632 | 71 | 25 | 0.026632 | 28.4 | 10 | 0.010653 | 8.52 | 3 | 0.0031958
|  | Sub Total |  |  |  | 284 |  | 5.68 |  |  | 28.4 |  |  | 71 |  |  | 71 |  |  | 71 |  |  | 28.4 |  |  | 8.52
Loan & Advance
4911 | 4911111 | Interest during Implementation |  |  |  | 6563 | 0.024617 | 131.26 | 2 | 0.049235 | 656.3 | 10 | 0.24617 | 1640.75 | 25 | 0.61544 | 1640.75 | 25 | 0.61544 | 1640.75 | 25 | 0.61544 | 656.3 | 10 | 0.24617 | 196.89 | 3 | 0.073852
|  | Sub Total |  |  |  | 6563 |  | 131.26 |  |  | 656.3 |  |  | 1640.75 |  |  | 1640.75 |  |  | 1640.75 |  |  | 656.3 |  |  | 196.89
|  | Total Capital Component: B |  |  |  | 213077 |  | 4261.54 |  |  | 21307.7 |  |  | 53269.25 |  |  | 53269.25 |  |  | 53269.25 |  |  | 21307.7 |  |  | 6392.31
|  | Total (A+B) |  |  |  | 240344.54 |  | 4806.8908 |  |  | 24034.454 |  |  | 60086.135 |  |  | 60086.135 |  |  | 60086.135 |  |  | 24034.454 |  |  | 7210.3362
|  | (C) Physical Contingency |  |  |  | 5013.46 | 0.018805 | 100.2692 | 2 | 0.03761 | 501.346 | 10 | 0.18805 | 1253.365 | 25 | 0.47013 | 1253.365 | 25 | 0.47013 | 1253.365 | 25 | 0.47013 | 501.346 | 10 | 0.18805 | 150.4038 | 3 | 0.056416
|  | (D) Price Contingency |  |  |  | 21242 | 0.079677 | 424.84 | 2 | 0.15935 | 2124.2 | 10 | 0.79677 | 5310.5 | 25 | 1.9919 | 5310.5 | 25 | 1.9919 | 5310.5 | 25 | 1.9919 | 2124.2 | 10 | 0.79677 | 637.26 | 3 | 0.23903
|  | Grand Total (A+B+C+D) |  |  |  | 266600 |  | 5332 |  |  | 26660 |  |  | 66650 |  |  | 66650 |  |  | 66650 |  |  | 26660 |  |  | 7998
| Weight of Each Item = |  | Est. Cost of Each Respective Item
Total Project Cost
| Physical Percentage (%) of Item = |  | Quantity of Item Targeted in Each Year | [5 empty] | X 100
Total Quantity of Respective Item for Whole Projecr Period
| Physical Percentage (%) of Total Project = |  | Weaight of Each Item x Phisical Percentage (%) of Item

## Annex-V (b)
[41 empty] | Annexure-V (b) | [24 empty] | Annexure-V (b)
Detail Annual Phasing Cost | [45 empty] | Detail Annual Phasing Cost
Name of the Project : Costal Towns Climate Resilience Project.
Name of Agency/Division/Ministry: LGED/LGD/LGRD&Co | [40 empty] | (Taka in lac) | [24 empty] | (Taka in lac)
Economic. Code | Economic Sub-Code | Economic Sub Code Description (in detail) | Unit | Unit Cost | Qunt. | Total DPP Cost | [7 empty] | Financial Year-1 | [7 empty] | Financial Year-2 | [7 empty] | Financial Year-3 | [7 empty] | Financial Year-4 | [7 empty] | Financial Year-5 | [7 empty] | Financial Year-6 | [7 empty] | Financial Year-7
[6 empty] | PA |  |  |  |  | Own fund | Others | Total | PA |  |  |  |  | Own fund | Others | Total | Cost |  |  |  |  | Own fund | Others | Total | Cost |  |  |  |  | Own fund | Others | Total | Cost |  |  |  |  | Own fund | Others | Total | Cost |  |  |  |  | Own fund | Others | Total | Cost |  |  |  |  | Own fund | Others | Total | Cost |  |  |  |  | Own fund | Others | Total
[6 empty] | GOB (FE) | RPA |  | DPA |  |  |  |  | GOB (FE) | RPA |  | DPA |  |  |  |  | GOB (FE) | RPA |  | DPA |  |  |  |  | GOB (FE) | RPA |  | DPA |  |  |  |  | GOB (FE) | RPA |  | DPA |  |  |  |  | GOB (FE) | RPA |  | DPA |  |  |  |  | GOB (FE) | RPA |  | DPA |  |  |  |  | GOB (FE) | RPA |  | DPA
[7 empty] | GOB | SP Acc.* | Through PD | Through DP |  |  |  |  | Through GOB | SP Acc. | Through PD | Through DP |  |  |  |  | Through GOB | SP Acc. | Through PD | Through DP |  |  |  |  | Through GOB | SP Acc. | Through PD | Through DP |  |  |  |  | Through GOB | SP Acc. | Through PD | Through DP |  |  |  |  | Through GOB | SP Acc. | Through PD | Through DP |  |  |  |  | Through GOB | SP Acc. | Through PD | Through DP |  |  |  |  | Through GOB | SP Acc. | Through PD | Through DP
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
(A) Revenue Component
Pay of Officer:
3111 | 3111101 | Basic Pay (Officer) | PM | 0.64 | 1932 | 1236.48 |  | 0 |  | 0 |  |  | 1236.48 | 24.7296 |  | 0 |  | 0 |  |  | 24.7296 | 123.648 |  | 0 |  | 0 |  |  | 123.648 | 309.12 |  | 0 |  | 0 |  |  | 309.12 | 309.12 |  | 0 |  | 0 |  |  | 309.12 | 309.12 |  | 0 |  | 0 |  |  | 309.12 | 123.648 |  | 0 |  | 0 |  |  | 123.648 | 37.0944 |  | 0 |  | 0 |  |  | 37.0944
|  | Sub Total |  |  |  | 1236.48 |  | 0 |  | 0 |  |  | 1236.48 | 24.7296 |  | 0 |  | 0 |  |  | 24.7296 | 123.648 |  | 0 |  | 0 |  |  | 123.648 | 309.12 |  | 0 |  | 0 |  |  | 309.12 | 309.12 |  | 0 |  | 0 |  |  | 309.12 | 309.12 |  | 0 |  | 0 |  |  | 309.12 | 123.648 |  | 0 |  | 0 |  |  | 123.648 | 37.0944 |  | 0 |  | 0 |  |  | 37.0944
Pay of Empolyee:
3111 | 3111201 | Basic Pay (Employee) | PM | 0.40478 | 504 | 204.01 |  | 0 |  | 0 |  |  | 204.01 | 4.0802 |  | 0 |  | 0 |  |  | 4.0802 | 20.401 |  | 0 |  | 0 |  |  | 20.401 | 51.0025 |  | 0 |  | 0 |  |  | 51.0025 | 51.0025 |  | 0 |  | 0 |  |  | 51.0025 | 51.0025 |  | 0 |  | 0 |  |  | 51.0025 | 20.401 |  | 0 |  | 0 |  |  | 20.401 | 6.1203 |  | 0 |  | 0 |  |  | 6.1203
|  | Sub Total |  |  |  | 204.01 |  | 0 |  | 0 |  |  | 204.01 | 4.0802 |  | 0 |  | 0 |  |  | 4.0802 | 20.401 |  | 0 |  | 0 |  |  | 20.401 | 51.0025 |  | 0 |  | 0 |  |  | 51.0025 | 51.0025 |  | 0 |  | 0 |  |  | 51.0025 | 51.0025 |  | 0 |  | 0 |  |  | 51.0025 | 20.401 |  | 0 |  | 0 |  |  | 20.401 | 6.1203 |  | 0 |  | 0 |  |  | 6.1203
Allowances:
3111 | 3111301 | Charge Allowance | PM | 0.057 | 420 | 23.94 |  | 0 |  | 0 |  |  | 23.94 | 0.4788 |  | 0 |  | 0 |  |  | 0.4788 | 2.394 |  | 0 |  | 0 |  |  | 2.394 | 5.985 |  | 0 |  | 0 |  |  | 5.985 | 5.985 |  | 0 |  | 0 |  |  | 5.985 | 5.985 |  | 0 |  | 0 |  |  | 5.985 | 2.394 |  | 0 |  | 0 |  |  | 2.394 | 0.7182 |  | 0 |  | 0 |  |  | 0.7182
3111 | 3111302 | Conveyance Allowance | PM | 0.0030159 | 504 | 1.52 |  | 0 |  | 0 |  |  | 1.52 | 0.0304 |  | 0 |  | 0 |  |  | 0.0304 | 0.152 |  | 0 |  | 0 |  |  | 0.152 | 0.38 |  | 0 |  | 0 |  |  | 0.38 | 0.38 |  | 0 |  | 0 |  |  | 0.38 | 0.38 |  | 0 |  | 0 |  |  | 0.38 | 0.152 |  | 0 |  | 0 |  |  | 0.152 | 0.0456 |  | 0 |  | 0 |  |  | 0.0456
3111 | 3111306 | Educational Allowance | PM | 0.0082759 | 2436 | 20.16 |  | 0 |  | 0 |  |  | 20.16 | 0.4032 |  | 0 |  | 0 |  |  | 0.4032 | 2.016 |  | 0 |  | 0 |  |  | 2.016 | 5.04 |  | 0 |  | 0 |  |  | 5.04 | 5.04 |  | 0 |  | 0 |  |  | 5.04 | 5.04 |  | 0 |  | 0 |  |  | 5.04 | 2.016 |  | 0 |  | 0 |  |  | 2.016 | 0.6048 |  | 0 |  | 0 |  |  | 0.6048
3111 | 3111310 | Housing Rent Allowances | PM | 0.35071 | 2436 | 854.34 |  | 0 |  | 0 |  |  | 854.34 | 17.0868 |  | 0 |  | 0 |  |  | 17.0868 | 85.434 |  | 0 |  | 0 |  |  | 85.434 | 213.585 |  | 0 |  | 0 |  |  | 213.585 | 213.585 |  | 0 |  | 0 |  |  | 213.585 | 213.585 |  | 0 |  | 0 |  |  | 213.585 | 85.434 |  | 0 |  | 0 |  |  | 85.434 | 25.6302 |  | 0 |  | 0 |  |  | 25.6302
3111 | 3111311 | Medical Allowance | PM | 0.015 | 2436 | 36.54 |  | 0 |  | 0 |  |  | 36.54 | 0.7308 |  | 0 |  | 0 |  |  | 0.7308 | 3.654 |  | 0 |  | 0 |  |  | 3.654 | 9.135 |  | 0 |  | 0 |  |  | 9.135 | 9.135 |  | 0 |  | 0 |  |  | 9.135 | 9.135 |  | 0 |  | 0 |  |  | 9.135 | 3.654 |  | 0 |  | 0 |  |  | 3.654 | 1.0962 |  | 0 |  | 0 |  |  | 1.0962
3111 | 3111312 | Mobile/Cell Phone Allowance | PM | 0.016 | 420 | 6.72 |  | 0 |  | 0 |  |  | 6.72 | 0.1344 |  | 0 |  | 0 |  |  | 0.1344 | 0.672 |  | 0 |  | 0 |  |  | 0.672 | 1.68 |  | 0 |  | 0 |  |  | 1.68 | 1.68 |  | 0 |  | 0 |  |  | 1.68 | 1.68 |  | 0 |  | 0 |  |  | 1.68 | 0.672 |  | 0 |  | 0 |  |  | 0.672 | 0.2016 |  | 0 |  | 0 |  |  | 0.2016
3111 | 3111314 | Tiffin Allowance | PM | 0.0030159 | 504 | 1.52 |  | 0 |  | 0 |  |  | 1.52 | 0.0304 |  | 0 |  | 0 |  |  | 0.0304 | 0.152 |  | 0 |  | 0 |  |  | 0.152 | 0.38 |  | 0 |  | 0 |  |  | 0.38 | 0.38 |  | 0 |  | 0 |  |  | 0.38 | 0.38 |  | 0 |  | 0 |  |  | 0.38 | 0.152 |  | 0 |  | 0 |  |  | 0.152 | 0.0456 |  | 0 |  | 0 |  |  | 0.0456
3111 | 3111325 | Festival Allowance | Nos. | 0.65195 | 435 | 283.6 |  | 0 |  | 0 |  |  | 283.6 | 5.672 |  | 0 |  | 0 |  |  | 5.672 | 28.36 |  | 0 |  | 0 |  |  | 28.36 | 70.9 |  | 0 |  | 0 |  |  | 70.9 | 70.9 |  | 0 |  | 0 |  |  | 70.9 | 70.9 |  | 0 |  | 0 |  |  | 70.9 | 28.36 |  | 0 |  | 0 |  |  | 28.36 | 8.508 |  | 0 |  | 0 |  |  | 8.508
3111 | 3111328 | Rest & Recreation Allowance | Nos. | 0.6 | 87 | 52.2 |  | 0 |  | 0 |  |  | 52.2 | 1.044 |  | 0 |  | 0 |  |  | 1.044 | 5.22 |  | 0 |  | 0 |  |  | 5.22 | 13.05 |  | 0 |  | 0 |  |  | 13.05 | 13.05 |  | 0 |  | 0 |  |  | 13.05 | 13.05 |  | 0 |  | 0 |  |  | 13.05 | 5.22 |  | 0 |  | 0 |  |  | 5.22 | 1.566 |  | 0 |  | 0 |  |  | 1.566
3111 | 3111335 | Bangla New Year Allowance | Nos. | 0.15 | 232 | 34.8 |  | 0 |  | 0 |  |  | 34.8 | 0.696 |  | 0 |  | 0 |  |  | 0.696 | 3.48 |  | 0 |  | 0 |  |  | 3.48 | 8.7 |  | 0 |  | 0 |  |  | 8.7 | 8.7 |  | 0 |  | 0 |  |  | 8.7 | 8.7 |  | 0 |  | 0 |  |  | 8.7 | 3.48 |  | 0 |  | 0 |  |  | 3.48 | 1.044 |  | 0 |  | 0 |  |  | 1.044
3111 | 3111338 | Other Allowance | L.S | 1.1903 | 232 | 276.16 |  | 0 |  | 0 |  |  | 276.16 | 5.5232 |  | 0 |  | 0 |  |  | 5.5232 | 27.616 |  | 0 |  | 0 |  |  | 27.616 | 69.04 |  | 0 |  | 0 |  |  | 69.04 | 69.04 |  | 0 |  | 0 |  |  | 69.04 | 69.04 |  | 0 |  | 0 |  |  | 69.04 | 27.616 |  | 0 |  | 0 |  |  | 27.616 | 8.2848 |  | 0 |  | 0 |  |  | 8.2848
|  | Sub Total |  |  |  | 1591.5 |  | 0 |  | 0 |  |  | 1591.5 | 31.83 |  | 0 |  | 0 |  |  | 31.83 | 159.15 |  | 0 |  | 0 |  |  | 159.15 | 397.875 |  | 0 |  | 0 |  |  | 397.875 | 397.875 |  | 0 |  | 0 |  |  | 397.875 | 397.875 |  | 0 |  | 0 |  |  | 397.875 | 159.15 |  | 0 |  | 0 |  |  | 159.15 | 47.745 |  | 0 |  | 0 |  |  | 47.745
Supplies and Services:
3211 | 3211111 | Seminar & Conference Expenses | Nos. | 7.6667 | 30 | 24.15 |  | 205.85 |  | 0 |  |  | 230 | 0.483 |  | 4.117 |  | 0 |  |  | 4.6 | 2.415 |  | 20.585 |  | 0 |  |  | 23 | 6.0375 |  | 51.4625 |  | 0 |  |  | 57.5 | 6.0375 |  | 51.4625 |  | 0 |  |  | 57.5 | 6.0375 |  | 51.4625 |  | 0 |  |  | 57.5 | 2.415 |  | 20.585 |  | 0 |  |  | 23 | 0.7245 |  | 6.1755 |  | 0 |  |  | 6.9
3211 | 3211113 | Electricity | Month | 2.8571 | 84 | 25.2 |  | 214.8 |  | 0 |  |  | 240 | 0.504 |  | 4.296 |  | 0 |  |  | 4.8 | 2.52 |  | 21.48 |  | 0 |  |  | 24 | 6.3 |  | 53.7 |  | 0 |  |  | 60 | 6.3 |  | 53.7 |  | 0 |  |  | 60 | 6.3 |  | 53.7 |  | 0 |  |  | 60 | 2.52 |  | 21.48 |  | 0 |  |  | 24 | 0.756 |  | 6.444 |  | 0 |  |  | 7.2
3211 | 3211119 | Postage | Month | 0.11905 | 84 | 1 |  | 9 |  | 0 |  |  | 10 | 0.02 |  | 0.18 |  | 0 |  |  | 0.2 | 0.1 |  | 0.9 |  | 0 |  |  | 1 | 0.25 |  | 2.25 |  | 0 |  |  | 2.5 | 0.25 |  | 2.25 |  | 0 |  |  | 2.5 | 0.25 |  | 2.25 |  | 0 |  |  | 2.5 | 0.1 |  | 0.9 |  | 0 |  |  | 1 | 0.03 |  | 0.27 |  | 0 |  |  | 0.3
3211 | 3211120 | Telephone | Month | 0.77381 | 84 | 6.82 |  | 58.18 |  | 0 |  |  | 65 | 0.1364 |  | 1.1636 |  | 0 |  |  | 1.3 | 0.682 |  | 5.818 |  | 0 |  |  | 6.5 | 1.705 |  | 14.545 |  | 0 |  |  | 16.25 | 1.705 |  | 14.545 |  | 0 |  |  | 16.25 | 1.705 |  | 14.545 |  | 0 |  |  | 16.25 | 0.682 |  | 5.818 |  | 0 |  |  | 6.5 | 0.2046 |  | 1.7454 |  | 0 |  |  | 1.95
3211 | 3211125 | Advertising Expenses | Nos. | 0.42035 | 678 | 29.92 |  | 255.08 |  | 0 |  |  | 285 | 0.5984 |  | 5.1016 |  | 0 |  |  | 5.7 | 2.992 |  | 25.508 |  | 0 |  |  | 28.5 | 7.48 |  | 63.77 |  | 0 |  |  | 71.25 | 7.48 |  | 63.77 |  | 0 |  |  | 71.25 | 7.48 |  | 63.77 |  | 0 |  |  | 71.25 | 2.992 |  | 25.508 |  | 0 |  |  | 28.5 | 0.8976 |  | 7.6524 |  | 0 |  |  | 8.55
3211 | 3211126 | Audio -VDO/Film Production | Nos. | 2.1739 | 23 | 5.25 |  | 44.75 |  | 0 |  |  | 50 | 0.105 |  | 0.895 |  | 0 |  |  | 1 | 0.525 |  | 4.475 |  | 0 |  |  | 5 | 1.3125 |  | 11.1875 |  | 0 |  |  | 12.5 | 1.3125 |  | 11.1875 |  | 0 |  |  | 12.5 | 1.3125 |  | 11.1875 |  | 0 |  |  | 12.5 | 0.525 |  | 4.475 |  | 0 |  |  | 5 | 0.1575 |  | 1.3425 |  | 0 |  |  | 1.5
3211 | 3211128 | Publications | L.S | 0 | 0 | 8.9 |  | 76.1 |  | 0 |  |  | 85 | 0.178 |  | 1.522 |  | 0 |  |  | 1.7 | 0.89 |  | 7.61 |  | 0 |  |  | 8.5 | 2.225 |  | 19.025 |  | 0 |  |  | 21.25 | 2.225 |  | 19.025 |  | 0 |  |  | 21.25 | 2.225 |  | 19.025 |  | 0 |  |  | 21.25 | 0.89 |  | 7.61 |  | 0 |  |  | 8.5 | 0.267 |  | 2.283 |  | 0 |  |  | 2.55
3211 | 3211131 | Out sourcing | PM | 0.35714 | 8820 | 330.75 |  | 2819.25 |  | 0 |  |  | 3150 | 6.615 |  | 56.385 |  | 0 |  |  | 63 | 33.075 |  | 281.925 |  | 0 |  |  | 315 | 82.6875 |  | 704.8125 |  | 0 |  |  | 787.5 | 82.6875 |  | 704.8125 |  | 0 |  |  | 787.5 | 82.6875 |  | 704.8125 |  | 0 |  |  | 787.5 | 33.075 |  | 281.925 |  | 0 |  |  | 315 | 9.9225 |  | 84.5775 |  | 0 |  |  | 94.5
3221 | 3221104 | Registration Fee | L.S | 0 | 0 | 34.1 |  | 290.8 |  | 0 |  |  | 324.9 | 0.682 |  | 5.816 |  | 0 |  |  | 6.498 | 3.41 |  | 29.08 |  | 0 |  |  | 32.49 | 8.525 |  | 72.7 |  | 0 |  |  | 81.225 | 8.525 |  | 72.7 |  | 0 |  |  | 81.225 | 8.525 |  | 72.7 |  | 0 |  |  | 81.225 | 3.41 |  | 29.08 |  | 0 |  |  | 32.49 | 1.023 |  | 8.724 |  | 0 |  |  | 9.747
3231 | 3231201 | DomesticTraining | Nos. | 7.5 | 50 | 39.35 |  | 335.65 |  | 0 |  |  | 375 | 0.787 |  | 6.713 |  | 0 |  |  | 7.5 | 3.935 |  | 33.565 |  | 0 |  |  | 37.5 | 9.8375 |  | 83.9125 |  | 0 |  |  | 93.75 | 9.8375 |  | 83.9125 |  | 0 |  |  | 93.75 | 9.8375 |  | 83.9125 |  | 0 |  |  | 93.75 | 3.935 |  | 33.565 |  | 0 |  |  | 37.5 | 1.1805 |  | 10.0695 |  | 0 |  |  | 11.25
3231 | 3231201 | ForeignTraining | Nos. | 116.6667 | 3 | 36.72 |  | 313.28 |  | 0 |  |  | 350 | 0.7344 |  | 6.2656 |  | 0 |  |  | 7 | 3.672 |  | 31.328 |  | 0 |  |  | 35 | 9.18 |  | 78.32 |  | 0 |  |  | 87.5 | 9.18 |  | 78.32 |  | 0 |  |  | 87.5 | 9.18 |  | 78.32 |  | 0 |  |  | 87.5 | 3.672 |  | 31.328 |  | 0 |  |  | 35 | 1.1016 |  | 9.3984 |  | 0 |  |  | 10.5
3241 | 3241101 | Domestic Travel Expenses | L.S | 0 | 0 | 38.34 |  | 326.41 |  | 0 |  |  | 364.75 | 0.7668 |  | 6.5282 |  | 0 |  |  | 7.295 | 3.834 |  | 32.641 |  | 0 |  |  | 36.475 | 9.585 |  | 81.6025 |  | 0 |  |  | 91.1875 | 9.585 |  | 81.6025 |  | 0 |  |  | 91.1875 | 9.585 |  | 81.6025 |  | 0 |  |  | 91.1875 | 3.834 |  | 32.641 |  | 0 |  |  | 36.475 | 1.1502 |  | 9.7923 |  | 0 |  |  | 10.9425
3241 | 3241102 | Domestic Trasfer Expenses | L.S | 0 | 0 | 5.25 |  | 44.75 |  | 0 |  |  | 50 | 0.105 |  | 0.895 |  | 0 |  |  | 1 | 0.525 |  | 4.475 |  | 0 |  |  | 5 | 1.3125 |  | 11.1875 |  | 0 |  |  | 12.5 | 1.3125 |  | 11.1875 |  | 0 |  |  | 12.5 | 1.3125 |  | 11.1875 |  | 0 |  |  | 12.5 | 0.525 |  | 4.475 |  | 0 |  |  | 5 | 0.1575 |  | 1.3425 |  | 0 |  |  | 1.5
3243 | 3243101 | Petrol, Oil and Lubricants | L.S | 0 | 0 | 89.25 |  | 760.75 |  | 0 |  |  | 850 | 1.785 |  | 15.215 |  | 0 |  |  | 17 | 8.925 |  | 76.075 |  | 0 |  |  | 85 | 22.3125 |  | 190.1875 |  | 0 |  |  | 212.5 | 22.3125 |  | 190.1875 |  | 0 |  |  | 212.5 | 22.3125 |  | 190.1875 |  | 0 |  |  | 212.5 | 8.925 |  | 76.075 |  | 0 |  |  | 85 | 2.6775 |  | 22.8225 |  | 0 |  |  | 25.5
3243 | 3243102 | Gas and Fuel | L.S | 0 | 0 | 56.7 |  | 483.3 |  | 0 |  |  | 540 | 1.134 |  | 9.666 |  | 0 |  |  | 10.8 | 5.67 |  | 48.33 |  | 0 |  |  | 54 | 14.175 |  | 120.825 |  | 0 |  |  | 135 | 14.175 |  | 120.825 |  | 0 |  |  | 135 | 14.175 |  | 120.825 |  | 0 |  |  | 135 | 5.67 |  | 48.33 |  | 0 |  |  | 54 | 1.701 |  | 14.499 |  | 0 |  |  | 16.2
3255 | 3255101 | Computer Consumables | L.S | 0 | 0 | 26.25 |  | 223.75 |  | 0 |  |  | 250 | 0.525 |  | 4.475 |  | 0 |  |  | 5 | 2.625 |  | 22.375 |  | 0 |  |  | 25 | 6.5625 |  | 55.9375 |  | 0 |  |  | 62.5 | 6.5625 |  | 55.9375 |  | 0 |  |  | 62.5 | 6.5625 |  | 55.9375 |  | 0 |  |  | 62.5 | 2.625 |  | 22.375 |  | 0 |  |  | 25 | 0.7875 |  | 6.7125 |  | 0 |  |  | 7.5
3255 | 3255104 | Stamps & Seals | L.S | 0 | 0 | 2.2 |  | 18.8 |  | 0 |  |  | 21 | 0.044 |  | 0.376 |  | 0 |  |  | 0.42 | 0.22 |  | 1.88 |  | 0 |  |  | 2.1 | 0.55 |  | 4.7 |  | 0 |  |  | 5.25 | 0.55 |  | 4.7 |  | 0 |  |  | 5.25 | 0.55 |  | 4.7 |  | 0 |  |  | 5.25 | 0.22 |  | 1.88 |  | 0 |  |  | 2.1 | 0.066 |  | 0.564 |  | 0 |  |  | 0.63
3255 | 3255105 | Others Stationery | L.S | 0 | 0 | 21.85 |  | 186.15 |  | 0 |  |  | 208 | 0.437 |  | 3.723 |  | 0 |  |  | 4.16 | 2.185 |  | 18.615 |  | 0 |  |  | 20.8 | 5.4625 |  | 46.5375 |  | 0 |  |  | 52 | 5.4625 |  | 46.5375 |  | 0 |  |  | 52 | 5.4625 |  | 46.5375 |  | 0 |  |  | 52 | 2.185 |  | 18.615 |  | 0 |  |  | 20.8 | 0.6555 |  | 5.5845 |  | 0 |  |  | 6.24
3257 | 3257101 | Consultancy | PM | 3.156 | 4544 | 3952 |  | 9739.65 |  | 649.35 |  |  | 14341 | 79.04 |  | 194.793 |  | 12.987 |  |  | 286.82 | 395.2 |  | 973.965 |  | 64.935 |  |  | 1434.1 | 988 |  | 2434.9125 |  | 162.3375 |  |  | 3585.25 | 988 |  | 2434.9125 |  | 162.3375 |  |  | 3585.25 | 988 |  | 2434.9125 |  | 162.3375 |  |  | 3585.25 | 395.2 |  | 973.965 |  | 64.935 |  |  | 1434.1 | 118.56 |  | 292.1895 |  | 19.4805 |  |  | 430.23
3257 | 3257104 | Survey | Nos. | 7.7809 | 110 | 89.7 |  | 766.2 |  | 0 |  |  | 855.9 | 1.794 |  | 15.324 |  | 0 |  |  | 17.118 | 8.97 |  | 76.62 |  | 0 |  |  | 85.59 | 22.425 |  | 191.55 |  | 0 |  |  | 213.975 | 22.425 |  | 191.55 |  | 0 |  |  | 213.975 | 22.425 |  | 191.55 |  | 0 |  |  | 213.975 | 8.97 |  | 76.62 |  | 0 |  |  | 85.59 | 2.691 |  | 22.986 |  | 0 |  |  | 25.677
3257 | 3257206 | Honorarium / Remuneration | Nos. | 0.33333 | 510 | 17.72 |  | 152.28 |  | 0 |  |  | 170 | 0.3544 |  | 3.0456 |  | 0 |  |  | 3.4 | 1.772 |  | 15.228 |  | 0 |  |  | 17 | 4.43 |  | 38.07 |  | 0 |  |  | 42.5 | 4.43 |  | 38.07 |  | 0 |  |  | 42.5 | 4.43 |  | 38.07 |  | 0 |  |  | 42.5 | 1.772 |  | 15.228 |  | 0 |  |  | 17 | 0.5316 |  | 4.5684 |  | 0 |  |  | 5.1
|  | Sub Total |  |  |  | 4841.42 |  | 17324.78 |  | 649.35 |  |  | 22815.55 | 96.8284 |  | 346.4956 |  | 12.987 |  |  | 456.311 | 484.142 |  | 1732.478 |  | 64.935 |  |  | 2281.555 | 1210.355 |  | 4331.195 |  | 162.3375 |  |  | 5703.8875 | 1210.355 |  | 4331.195 |  | 162.3375 |  |  | 5703.8875 | 1210.355 |  | 4331.195 |  | 162.3375 |  |  | 5703.8875 | 484.142 |  | 1732.478 |  | 64.935 |  |  | 2281.555 | 145.2426 |  | 519.7434 |  | 19.4805 |  |  | 684.4665
Repair, Maintenance and Rehabilitation
3258 | 3258101 | Motor Vehicle | L.S | 0 | 0 | 143.6 |  | 918.4 |  | 0 |  |  | 1062 | 2.872 |  | 18.368 |  | 0 |  |  | 21.24 | 14.36 |  | 91.84 |  | 0 |  |  | 106.2 | 35.9 |  | 229.6 |  | 0 |  |  | 265.5 | 35.9 |  | 229.6 |  | 0 |  |  | 265.5 | 35.9 |  | 229.6 |  | 0 |  |  | 265.5 | 14.36 |  | 91.84 |  | 0 |  |  | 106.2 | 4.308 |  | 27.552 |  | 0 |  |  | 31.86
3258 | 3258102 | Furniture | L.S | 0 | 0 | 18.66 |  | 119.34 |  | 0 |  |  | 138 | 0.3732 |  | 2.3868 |  | 0 |  |  | 2.76 | 1.866 |  | 11.934 |  | 0 |  |  | 13.8 | 4.665 |  | 29.835 |  | 0 |  |  | 34.5 | 4.665 |  | 29.835 |  | 0 |  |  | 34.5 | 4.665 |  | 29.835 |  | 0 |  |  | 34.5 | 1.866 |  | 11.934 |  | 0 |  |  | 13.8 | 0.5598 |  | 3.5802 |  | 0 |  |  | 4.14
3258 | 3258103 | Computer | L.S | 0 | 0 | 14.87 |  | 95.13 |  | 0 |  |  | 110 | 0.2974 |  | 1.9026 |  | 0 |  |  | 2.2 | 1.487 |  | 9.513 |  | 0 |  |  | 11 | 3.7175 |  | 23.7825 |  | 0 |  |  | 27.5 | 3.7175 |  | 23.7825 |  | 0 |  |  | 27.5 | 3.7175 |  | 23.7825 |  | 0 |  |  | 27.5 | 1.487 |  | 9.513 |  | 0 |  |  | 11 | 0.4461 |  | 2.8539 |  | 0 |  |  | 3.3
3258 | 3258105 | Machinaris and Equipment | L.S | 0 | 0 | 14.87 |  | 95.13 |  | 0 |  |  | 110 | 0.2974 |  | 1.9026 |  | 0 |  |  | 2.2 | 1.487 |  | 9.513 |  | 0 |  |  | 11 | 3.7175 |  | 23.7825 |  | 0 |  |  | 27.5 | 3.7175 |  | 23.7825 |  | 0 |  |  | 27.5 | 3.7175 |  | 23.7825 |  | 0 |  |  | 27.5 | 1.487 |  | 9.513 |  | 0 |  |  | 11 | 0.4461 |  | 2.8539 |  | 0 |  |  | 3.3
|  | Sub Total |  |  |  | 192 |  | 1228 |  | 0 |  |  | 1420 | 3.84 |  | 24.56 |  | 0 |  |  | 28.4 | 19.2 |  | 122.8 |  | 0 |  |  | 142 | 48 |  | 307 |  | 0 |  |  | 355 | 48 |  | 307 |  | 0 |  |  | 355 | 48 |  | 307 |  | 0 |  |  | 355 | 19.2 |  | 122.8 |  | 0 |  |  | 142 | 5.76 |  | 36.84 |  | 0 |  |  | 42.6
|  | Total Revenue Component: A |  |  |  | 8065.41 |  | 18552.78 |  | 649.35 |  |  | 27267.54 | 161.3082 |  | 371.0556 |  | 12.987 |  |  | 545.3508 | 806.541 |  | 1855.278 |  | 64.935 |  |  | 2726.754 | 2016.3525 |  | 4638.195 |  | 162.3375 |  |  | 6816.885 | 2016.3525 |  | 4638.195 |  | 162.3375 |  |  | 6816.885 | 2016.3525 |  | 4638.195 |  | 162.3375 |  |  | 6816.885 | 806.541 |  | 1855.278 |  | 64.935 |  |  | 2726.754 | 241.9623 |  | 556.5834 |  | 19.4805 |  |  | 818.0262
(B) Capital Component
Acquisition of Assets
4112 | 4112101 | Jeep | Nos | 100 | 7 | 73.5 |  | 626.5 |  | 0 |  |  | 700 | 1.47 |  | 12.53 |  | 0 |  |  | 14 | 7.35 |  | 62.65 |  | 0 |  |  | 70 | 18.375 |  | 156.625 |  | 0 |  |  | 175 | 18.375 |  | 156.625 |  | 0 |  |  | 175 | 18.375 |  | 156.625 |  | 0 |  |  | 175 | 7.35 |  | 62.65 |  | 0 |  |  | 70 | 2.205 |  | 18.795 |  | 0 |  |  | 21
4112 | 4112101 | Double Cabin Pickup/ Carryboy | Nos | 76.661 | 29 | 233.28 |  | 1989.89 |  | 0 |  |  | 2223.17 | 4.6656 |  | 39.7978 |  | 0 |  |  | 44.4634 | 23.328 |  | 198.989 |  | 0 |  |  | 222.317 | 58.32 |  | 497.4725 |  | 0 |  |  | 555.7925 | 58.32 |  | 497.4725 |  | 0 |  |  | 555.7925 | 58.32 |  | 497.4725 |  | 0 |  |  | 555.7925 | 23.328 |  | 198.989 |  | 0 |  |  | 222.317 | 6.9984 |  | 59.6967 |  | 0 |  |  | 66.6951
4112 | 4112101 | Micro Bus | Nos | 76.515 | 2 | 16.07 |  | 136.96 |  | 0 |  |  | 153.03 | 0.3214 |  | 2.7392 |  | 0 |  |  | 3.0606 | 1.607 |  | 13.696 |  | 0 |  |  | 15.303 | 4.0175 |  | 34.24 |  | 0 |  |  | 38.2575 | 4.0175 |  | 34.24 |  | 0 |  |  | 38.2575 | 4.0175 |  | 34.24 |  | 0 |  |  | 38.2575 | 1.607 |  | 13.696 |  | 0 |  |  | 15.303 | 0.4821 |  | 4.1088 |  | 0 |  |  | 4.5909
4112 | 4112101 | Motor Cycle | Nos | 2.5521 | 24 | 6.48 |  | 54.77 |  | 0 |  |  | 61.25 | 0.1296 |  | 1.0954 |  | 0 |  |  | 1.225 | 0.648 |  | 5.477 |  | 0 |  |  | 6.125 | 1.62 |  | 13.6925 |  | 0 |  |  | 15.3125 | 1.62 |  | 13.6925 |  | 0 |  |  | 15.3125 | 1.62 |  | 13.6925 |  | 0 |  |  | 15.3125 | 0.648 |  | 5.477 |  | 0 |  |  | 6.125 | 0.1944 |  | 1.6431 |  | 0 |  |  | 1.8375
4112 | 4112202 | Computers and Accessories | Nos | 1.994 | 163 | 34.12 |  | 290.91 |  | 0 |  |  | 325.03 | 0.6824 |  | 5.8182 |  | 0 |  |  | 6.5006 | 3.412 |  | 29.091 |  | 0 |  |  | 32.503 | 8.53 |  | 72.7275 |  | 0 |  |  | 81.2575 | 8.53 |  | 72.7275 |  | 0 |  |  | 81.2575 | 8.53 |  | 72.7275 |  | 0 |  |  | 81.2575 | 3.412 |  | 29.091 |  | 0 |  |  | 32.503 | 1.0236 |  | 8.7273 |  | 0 |  |  | 9.7509
4112 | 4112304 | Engineering and other Equipments | Nos/Set | 8.5387 | 660 | 591.73 |  | 5043.79 |  | 0 |  |  | 5635.52 | 11.8346 |  | 100.8758 |  | 0 |  |  | 112.7104 | 59.173 |  | 504.379 |  | 0 |  |  | 563.552 | 147.9325 |  | 1260.9475 |  | 0 |  |  | 1408.88 | 147.9325 |  | 1260.9475 |  | 0 |  |  | 1408.88 | 147.9325 |  | 1260.9475 |  | 0 |  |  | 1408.88 | 59.173 |  | 504.379 |  | 0 |  |  | 563.552 | 17.7519 |  | 151.3137 |  | 0 |  |  | 169.0656
4112 | 4112314 | Furniture | L.S | 0 | 0 | 15.95 |  | 136.05 |  | 0 |  |  | 152 | 0.319 |  | 2.721 |  | 0 |  |  | 3.04 | 1.595 |  | 13.605 |  | 0 |  |  | 15.2 | 3.9875 |  | 34.0125 |  | 0 |  |  | 38 | 3.9875 |  | 34.0125 |  | 0 |  |  | 38 | 3.9875 |  | 34.0125 |  | 0 |  |  | 38 | 1.595 |  | 13.605 |  | 0 |  |  | 15.2 | 0.4785 |  | 4.0815 |  | 0 |  |  | 4.56
|  | Sub Total |  |  |  | 971.13 |  | 8278.87 |  | 0 |  |  | 9250 | 19.4226 |  | 165.5774 |  | 0 |  |  | 185 | 97.113 |  | 827.887 |  | 0 |  |  | 925 | 242.7825 |  | 2069.7175 |  | 0 |  |  | 2312.5 | 242.7825 |  | 2069.7175 |  | 0 |  |  | 2312.5 | 242.7825 |  | 2069.7175 |  | 0 |  |  | 2312.5 | 97.113 |  | 827.887 |  | 0 |  |  | 925 | 29.1339 |  | 248.3661 |  | 0 |  |  | 277.5
4141 | 4141101 | Land Acquisition & Resettlement (Compensation for Land, structure & other assets including re-location, transitional training, vulnerable, documentation, monitoring, mitigation capacity measures & all other cost related to address ADB Safeguard issues) | Acre | 158.401 | 66.54 | 10540 |  | 0 |  | 0 |  |  | 10540 | 210.8 |  | 0 |  | 0 |  |  | 210.8 | 1054 |  | 0 |  | 0 |  |  | 1054 | 2635 |  | 0 |  | 0 |  |  | 2635 | 2635 |  | 0 |  | 0 |  |  | 2635 | 2635 |  | 0 |  | 0 |  |  | 2635 | 1054 |  | 0 |  | 0 |  |  | 1054 | 316.2 |  | 0 |  | 0 |  |  | 316.2
|  | Sub Total |  |  |  | 10540 |  | 0 |  | 0 |  |  | 10540 | 210.8 |  | 0 |  | 0 |  |  | 210.8 | 1054 |  | 0 |  | 0 |  |  | 1054 | 2635 |  | 0 |  | 0 |  |  | 2635 | 2635 |  | 0 |  | 0 |  |  | 2635 | 2635 |  | 0 |  | 0 |  |  | 2635 | 1054 |  | 0 |  | 0 |  |  | 1054 | 316.2 |  | 0 |  | 0 |  |  | 316.2
Construction of Works
Stage-I
4111 | 4111304 | Roads | Km | 238.9632 | 298.387 | 8912.94 |  | 62390.56 |  | 0 |  |  | 71303.5 | 178.2588 |  | 1247.8112 |  | 0 |  |  | 1426.07 | 891.294 |  | 6239.056 |  | 0 |  |  | 7130.35 | 2228.235 |  | 15597.64 |  | 0 |  |  | 17825.875 | 2228.235 |  | 15597.64 |  | 0 |  |  | 17825.875 | 2228.235 |  | 15597.64 |  | 0 |  |  | 17825.875 | 891.294 |  | 6239.056 |  | 0 |  |  | 7130.35 | 267.3882 |  | 1871.7168 |  | 0 |  |  | 2139.105
4111 | 4111303 | Bridges | m | 13.9576 | 920 | 1605.13 |  | 11235.88 |  | 0 |  |  | 12841.01 | 32.1026 |  | 224.7176 |  | 0 |  |  | 256.8202 | 160.513 |  | 1123.588 |  | 0 |  |  | 1284.101 | 401.2825 |  | 2808.97 |  | 0 |  |  | 3210.2525 | 401.2825 |  | 2808.97 |  | 0 |  |  | 3210.2525 | 401.2825 |  | 2808.97 |  | 0 |  |  | 3210.2525 | 160.513 |  | 1123.588 |  | 0 |  |  | 1284.101 | 48.1539 |  | 337.0764 |  | 0 |  |  | 385.2303
4111 | 4111307 | Drainage & Flood Control | Km | 334.3158 | 140.97 | 5891.06 |  | 41237.44 |  | 0 |  |  | 47128.5 | 117.8212 |  | 824.7488 |  | 0 |  |  | 942.57 | 589.106 |  | 4123.744 |  | 0 |  |  | 4712.85 | 1472.765 |  | 10309.36 |  | 0 |  |  | 11782.125 | 1472.765 |  | 10309.36 |  | 0 |  |  | 11782.125 | 1472.765 |  | 10309.36 |  | 0 |  |  | 11782.125 | 589.106 |  | 4123.744 |  | 0 |  |  | 4712.85 | 176.7318 |  | 1237.1232 |  | 0 |  |  | 1413.855
Others Structures
4111 | 4111317 | (a) Cyclone Shelters | Nos. | 464.9435 | 23 | 1336.71 |  | 9356.99 |  | 0 |  |  | 10693.7 | 26.7342 |  | 187.1398 |  | 0 |  |  | 213.874 | 133.671 |  | 935.699 |  | 0 |  |  | 1069.37 | 334.1775 |  | 2339.2475 |  | 0 |  |  | 2673.425 | 334.1775 |  | 2339.2475 |  | 0 |  |  | 2673.425 | 334.1775 |  | 2339.2475 |  | 0 |  |  | 2673.425 | 133.671 |  | 935.699 |  | 0 |  |  | 1069.37 | 40.1013 |  | 280.7097 |  | 0 |  |  | 320.811
4111 | 4111317 | (b) Solid Waste Management | Nos. | 2125 | 4 | 1062.5 |  | 7437.5 |  | 0 |  |  | 8500 | 21.25 |  | 148.75 |  | 0 |  |  | 170 | 106.25 |  | 743.75 |  | 0 |  |  | 850 | 265.625 |  | 1859.375 |  | 0 |  |  | 2125 | 265.625 |  | 1859.375 |  | 0 |  |  | 2125 | 265.625 |  | 1859.375 |  | 0 |  |  | 2125 | 106.25 |  | 743.75 |  | 0 |  |  | 850 | 31.875 |  | 223.125 |  | 0 |  |  | 255
4111 | 4111317 | (c) Green Space | Nos. | 750 | 2 | 187.5 |  | 1312.5 |  | 0 |  |  | 1500 | 3.75 |  | 26.25 |  | 0 |  |  | 30 | 18.75 |  | 131.25 |  | 0 |  |  | 150 | 46.875 |  | 328.125 |  | 0 |  |  | 375 | 46.875 |  | 328.125 |  | 0 |  |  | 375 | 46.875 |  | 328.125 |  | 0 |  |  | 375 | 18.75 |  | 131.25 |  | 0 |  |  | 150 | 5.625 |  | 39.375 |  | 0 |  |  | 45
4111 | 4111317 | (d) Nature-Base Solution | Nos. | 760 | 3 | 285 |  | 1995 |  | 0 |  |  | 2280 | 5.7 |  | 39.9 |  | 0 |  |  | 45.6 | 28.5 |  | 199.5 |  | 0 |  |  | 228 | 71.25 |  | 498.75 |  | 0 |  |  | 570 | 71.25 |  | 498.75 |  | 0 |  |  | 570 | 71.25 |  | 498.75 |  | 0 |  |  | 570 | 28.5 |  | 199.5 |  | 0 |  |  | 228 | 8.55 |  | 59.85 |  | 0 |  |  | 68.4
4111 | 4111317 | (e) Slum Improvement | Nos. | 79.5455 | 22 | 218.75 |  | 1531.25 |  | 0 |  |  | 1750 | 4.375 |  | 30.625 |  | 0 |  |  | 35 | 21.875 |  | 153.125 |  | 0 |  |  | 175 | 54.6875 |  | 382.8125 |  | 0 |  |  | 437.5 | 54.6875 |  | 382.8125 |  | 0 |  |  | 437.5 | 54.6875 |  | 382.8125 |  | 0 |  |  | 437.5 | 21.875 |  | 153.125 |  | 0 |  |  | 175 | 6.5625 |  | 45.9375 |  | 0 |  |  | 52.5
Stage-II
Others Structures
4111 | 4111317 | (a) Multipurpose Market | Nos. | 564.8571 | 21 | 1482.75 |  | 10379.25 |  | 0 |  |  | 11862 | 29.655 |  | 207.585 |  | 0 |  |  | 237.24 | 148.275 |  | 1037.925 |  | 0 |  |  | 1186.2 | 370.6875 |  | 2594.8125 |  | 0 |  |  | 2965.5 | 370.6875 |  | 2594.8125 |  | 0 |  |  | 2965.5 | 370.6875 |  | 2594.8125 |  | 0 |  |  | 2965.5 | 148.275 |  | 1037.925 |  | 0 |  |  | 1186.2 | 44.4825 |  | 311.3775 |  | 0 |  |  | 355.86
4111 | 4111317 | (b) Bus Terminal | Nos. | 2125 | 4 | 1062.5 |  | 7437.5 |  | 0 |  |  | 8500 | 21.25 |  | 148.75 |  | 0 |  |  | 170 | 106.25 |  | 743.75 |  | 0 |  |  | 850 | 265.625 |  | 1859.375 |  | 0 |  |  | 2125 | 265.625 |  | 1859.375 |  | 0 |  |  | 2125 | 265.625 |  | 1859.375 |  | 0 |  |  | 2125 | 106.25 |  | 743.75 |  | 0 |  |  | 850 | 31.875 |  | 223.125 |  | 0 |  |  | 255
4111 | 4111317 | (c) Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/ Bus Bay/Poltun etc. | Nos. | 458.2405 | 22 | 1260.16 |  | 8821.13 |  | 0 |  |  | 10081.29 | 25.2032 |  | 176.4226 |  | 0 |  |  | 201.6258 | 126.016 |  | 882.113 |  | 0 |  |  | 1008.129 | 315.04 |  | 2205.2825 |  | 0 |  |  | 2520.3225 | 315.04 |  | 2205.2825 |  | 0 |  |  | 2520.3225 | 315.04 |  | 2205.2825 |  | 0 |  |  | 2520.3225 | 126.016 |  | 882.113 |  | 0 |  |  | 1008.129 | 37.8048 |  | 264.6339 |  | 0 |  |  | 302.4387
|  | Sub Total |  |  |  | 23305 |  | 163135 |  | 0 |  |  | 186440 | 466.1 |  | 3262.7 |  | 0 |  |  | 3728.8 | 2330.5 |  | 16313.5 |  | 0 |  |  | 18644 | 5826.25 |  | 40783.75 |  | 0 |  |  | 46610 | 5826.25 |  | 40783.75 |  | 0 |  |  | 46610 | 5826.25 |  | 40783.75 |  | 0 |  |  | 46610 | 2330.5 |  | 16313.5 |  | 0 |  |  | 18644 | 699.15 |  | 4894.05 |  | 0 |  |  | 5593.2
Block Allocation
4911 | 4911111 | Block Allocation (Commitment Charge) |  |  |  | 284 |  | 0 |  | 0 |  |  | 284 | 5.68 |  | 0 |  | 0 |  |  | 5.68 | 28.4 |  | 0 |  | 0 |  |  | 28.4 | 71 |  | 0 |  | 0 |  |  | 71 | 71 |  | 0 |  | 0 |  |  | 71 | 71 |  | 0 |  | 0 |  |  | 71 | 28.4 |  | 0 |  | 0 |  |  | 28.4 | 8.52 |  | 0 |  | 0 |  |  | 8.52
|  | Sub Total |  |  |  | 284 |  | 0 |  | 0 |  |  | 284 | 5.68 |  | 0 |  | 0 |  |  | 5.68 | 28.4 |  | 0 |  | 0 |  |  | 28.4 | 71 |  | 0 |  | 0 |  |  | 71 | 71 |  | 0 |  | 0 |  |  | 71 | 71 |  | 0 |  | 0 |  |  | 71 | 28.4 |  | 0 |  | 0 |  |  | 28.4 | 8.52 |  | 0 |  | 0 |  |  | 8.52
Loan & Advance
7215 | 7215205 | Interest during Implementation |  |  |  | 6563 |  | 0 |  | 0 |  |  | 6563 | 131.26 |  | 0 |  | 0 |  |  | 131.26 | 656.3 |  | 0 |  | 0 |  |  | 656.3 | 1640.75 |  | 0 |  | 0 |  |  | 1640.75 | 1640.75 |  | 0 |  | 0 |  |  | 1640.75 | 1640.75 |  | 0 |  | 0 |  |  | 1640.75 | 656.3 |  | 0 |  | 0 |  |  | 656.3 | 196.89 |  | 0 |  | 0 |  |  | 196.89
|  | Sub Total |  |  |  | 6563 |  | 0 |  | 0 |  |  | 6563 | 131.26 |  | 0 |  | 0 |  |  | 131.26 | 656.3 |  | 0 |  | 0 |  |  | 656.3 | 1640.75 |  | 0 |  | 0 |  |  | 1640.75 | 1640.75 |  | 0 |  | 0 |  |  | 1640.75 | 1640.75 |  | 0 |  | 0 |  |  | 1640.75 | 656.3 |  | 0 |  | 0 |  |  | 656.3 | 196.89 |  | 0 |  | 0 |  |  | 196.89
|  | Total Capital Component: B |  |  |  | 41663.13 |  | 171413.87 |  | 0 |  |  | 213077 | 833.2626 |  | 3428.2774 |  | 0 |  |  | 4261.54 | 4166.313 |  | 17141.387 |  | 0 |  |  | 21307.7 | 10415.7825 |  | 42853.4675 |  | 0 |  |  | 53269.25 | 10415.7825 |  | 42853.4675 |  | 0 |  |  | 53269.25 | 10415.7825 |  | 42853.4675 |  | 0 |  |  | 53269.25 | 4166.313 |  | 17141.387 |  | 0 |  |  | 21307.7 | 1249.8939 |  | 5142.4161 |  | 0 |  |  | 6392.31
|  | Total (A+B) |  |  |  | 49728.54 |  | 189966.65 |  | 649.35 |  |  | 240344.54 | 994.5708 |  | 3799.333 |  | 12.987 |  |  | 4806.8908 | 4972.854 |  | 18996.665 |  | 64.935 |  |  | 24034.454 | 12432.135 |  | 47491.6625 |  | 162.3375 |  |  | 60086.135 | 12432.135 |  | 47491.6625 |  | 162.3375 |  |  | 60086.135 | 12432.135 |  | 47491.6625 |  | 162.3375 |  |  | 60086.135 | 4972.854 |  | 18996.665 |  | 64.935 |  |  | 24034.454 | 1491.8562 |  | 5698.9995 |  | 19.4805 |  |  | 7210.3362
|  | (C) Physical Contingency |  |  |  | 1871.46 |  | 3142 |  | 0 |  |  | 5013.46 | 37.4292 |  | 62.84 |  | 0 |  |  | 100.2692 | 187.146 |  | 314.2 |  | 0 |  |  | 501.346 | 467.865 |  | 785.5 |  | 0 |  |  | 1253.365 | 467.865 |  | 785.5 |  | 0 |  |  | 1253.365 | 467.865 |  | 785.5 |  | 0 |  |  | 1253.365 | 187.146 |  | 314.2 |  | 0 |  |  | 501.346 | 56.1438 |  | 94.26 |  | 0 |  |  | 150.4038
|  | (D) Price Contingency |  |  |  | 0 |  | 21242 |  | 0 |  |  | 21242 | 0 |  | 424.84 |  | 0 |  |  | 424.84 | 0 |  | 2124.2 |  | 0 |  |  | 2124.2 | 0 |  | 5310.5 |  | 0 |  |  | 5310.5 | 0 |  | 5310.5 |  | 0 |  |  | 5310.5 | 0 |  | 5310.5 |  | 0 |  |  | 5310.5 | 0 |  | 2124.2 |  | 0 |  |  | 2124.2 | 0 |  | 637.26 |  | 0 |  |  | 637.26
|  | Grand Total (A+B+C+D) |  |  |  | 51600 |  | 214350.65 |  | 649.35 |  |  | 266600 | 1032 |  | 4287.013 |  | 12.987 |  |  | 5332 | 5160 |  | 21435.065 |  | 64.935 |  |  | 26660 | 12900 |  | 53587.6625 |  | 162.3375 |  |  | 66650 | 12900 |  | 53587.6625 |  | 162.3375 |  |  | 66650 | 12900 |  | 53587.6625 |  | 162.3375 |  |  | 66650 | 5160 |  | 21435.065 |  | 64.935 |  |  | 26660 | 1548 |  | 6430.5195 |  | 19.4805 |  |  | 7998

## Annex-V (a)
Annuxture-V (a)
Detail Estimate Cost
Name of the Project: Costal Towns Climate Resilience Project.
Name of Agency/Division/Ministry: LGED/LGD/LGRD&Co
(Taka in Lac)
Economic Code | Economic Sub-Code | Economic Sub-Code Description (in detail) | Unit | Unit Cost | Quantity | Total | [7 empty] | % of total project cost
[6 empty] | GOB (FE) | PA |  |  |  | Own fund | Others | Total
RPA
[7 empty] | GOB | SP Acc.* | Through PD | Through DP
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
(A) Revenue Component
Pay of Officer:
3111 | 3111101 | Basic Pay (Officer) | PM | 0.64 | 1932 | 1236.48 |  | 0 |  | 0 |  |  | 1236.48 | 0.004638
|  | Sub Total |  |  |  | 1236.48 |  | 0 |  | 0 |  |  | 1236.48 | 0.004638
|  | Pay of Employee: | [5 empty] | 0
3111 | 3111201 | Basic Pay (Employee) | PM | 0.40478 | 504 | 204.01 |  | 0 |  | 0 |  |  | 204.01 | 0.00076523
|  | Sub Total |  |  |  | 204.01 |  | 0 |  | 0 |  |  | 204.01 | 0.00076523
Allowances:
3111 | 3111301 | Charge Allowance | PM | 0.057 | 420 | 23.94 |  | 0 |  | 0 |  |  | 23.94 | 8.9797e-05
3111 | 3111302 | Conveyance Allowance | PM | 0.0030159 | 504 | 1.52 |  | 0 |  | 0 |  |  | 1.52 | 5.7014e-06
3111 | 3111306 | Educational Allowance | PM | 0.0082759 | 2436 | 20.16 |  | 0 |  | 0 |  |  | 20.16 | 7.5619e-05
3111 | 3111310 | Housing Rent Allowances | PM | 0.35071 | 2436 | 854.34 |  | 0 |  | 0 |  |  | 854.34 | 0.0032046
3111 | 3111311 | Medical Allowance | PM | 0.015 | 2436 | 36.54 |  | 0 |  | 0 |  |  | 36.54 | 0.00013706
3111 | 3111312 | Mobile/Cell Phone Allowance | PM | 0.016 | 420 | 6.72 |  | 0 |  | 0 |  |  | 6.72 | 2.5206e-05
3111 | 3111314 | Tiffin Allowance | PM | 0.0030159 | 504 | 1.52 |  | 0 |  | 0 |  |  | 1.52 | 5.7014e-06
3111 | 3111325 | Festival Allowance | Nos. | 0.65195 | 435 | 283.6 |  | 0 |  | 0 |  |  | 283.6 | 0.0010638
3111 | 3111328 | Rest & Recreation Allowance | Nos. | 0.6 | 87 | 52.2 |  | 0 |  | 0 |  |  | 52.2 | 0.0001958
3111 | 3111335 | Bangla New Year Allowance | Nos. | 0.15 | 232 | 34.8 |  | 0 |  | 0 |  |  | 34.8 | 0.00013053
3111 | 3111338 | Other Allowance | L.S | 1.1903 | 232 | 276.16 |  | 0 |  | 0 |  |  | 276.16 | 0.0010359
|  | Sub Total |  |  |  | 1591.5 |  | 0 |  | 0 |  |  | 1591.5 | 0.0059696
Supplies and Services:
3211 | 3211111 | Seminar & Conference Expenses | Nos. | 7.6667 | 30 | 24.15 |  | 205.85 |  | 0 |  |  | 230 | 0.00086272
3211 | 3211113 | Electricity | Month | 2.8571 | 84 | 25.2 |  | 214.8 |  | 0 |  |  | 240 | 0.00090023
3211 | 3211119 | Postage | Month | 0.11905 | 84 | 1 |  | 9 |  | 0 |  |  | 10 | 3.7509e-05
3211 | 3211120 | Telephone | Month | 0.77381 | 84 | 6.82 |  | 58.18 |  | 0 |  |  | 65 | 0.00024381
3211 | 3211125 | Advertising Expenses | Nos. | 0.42035 | 678 | 29.92 |  | 255.08 |  | 0 |  |  | 285 | 0.001069
3211 | 3211126 | Audio -VDO/Film Production | Nos. | 2.1739 | 23 | 5.25 |  | 44.75 |  | 0 |  |  | 50 | 0.00018755
3211 | 3211128 | Publications | L.S | 0 | 0 | 8.9 |  | 76.1 |  | 0 |  |  | 85 | 0.00031883
3211 | 3211131 | Out sourcing | PM | 0.35714 | 8820 | 330.75 |  | 2819.25 |  | 0 |  |  | 3150 | 0.011815
3221 | 3221104 | Registration Fee | L.S | 0 | 0 | 34.1 |  | 290.8 |  | 0 |  |  | 324.9 | 0.0012187
3231 | 3231201 | DomesticTraining | Nos. | 7.5 | 50 | 39.35 |  | 335.65 |  | 0 |  |  | 375 | 0.0014066
3231 | 3231101 | ForeignTraining | Nos. | 116.6667 | 3 | 36.72 |  | 313.28 |  | 0 |  |  | 350 | 0.0013128
3241 | 3241101 | Domestic Travel Expenses | L.S | 0 | 0 | 38.34 |  | 326.41 |  | 0 |  |  | 364.75 | 0.0013682
3241 | 3241102 | Domestic Trasfer Expenses | L.S | 0 | 0 | 5.25 |  | 44.75 |  | 0 |  |  | 50 | 0.00018755
3243 | 3243101 | Petrol, Oil and Lubricants | L.S | 0 | 0 | 89.25 |  | 760.75 |  | 0 |  |  | 850 | 0.0031883
3243 | 3243102 | Gas and Fuel | L.S | 0 | 0 | 56.7 |  | 483.3 |  | 0 |  |  | 540 | 0.0020255
3255 | 3255101 | Computer Consumables | L.S | 0 | 0 | 26.25 |  | 223.75 |  | 0 |  |  | 250 | 0.00093773
3255 | 3255104 | Stamps & Seals | L.S | 0 | 0 | 2.2 |  | 18.8 |  | 0 |  |  | 21 | 7.877e-05
3255 | 3255105 | Others Stationery | L.S | 0 | 0 | 21.85 |  | 186.15 |  | 0 |  |  | 208 | 0.0007802
3257 | 3257101 | Consultancy | PM | 3.156 | 4544 | 3952 |  | 9739.65 |  | 649.35 |  |  | 14341 | 0.053792
3257 | 3257104 | Survey | Nos. | 7.7809 | 110 | 89.7 |  | 766.2 |  | 0 |  |  | 855.9 | 0.0032104
3257 | 3257206 | Honorarium / Remuneration | Nos. | 0.33333 | 510 | 17.72 |  | 152.28 |  | 0 |  |  | 170 | 0.00063766
|  | Sub Total |  |  |  | 4841.42 |  | 17324.78 |  | 649.35 |  |  | 22815.55 | 0.08558
Repair, Maintenance and Rehabilitation
3258 | 3258101 | Motor Vehicle | L.S | 0 | 0 | 143.6 |  | 918.4 |  | 0 |  |  | 1062 | 0.0039835
3258 | 3258102 | Furniture | L.S | 0 | 0 | 18.66 |  | 119.34 |  | 0 |  |  | 138 | 0.00051763
3258 | 3258103 | Computer | L.S | 0 | 0 | 14.87 |  | 95.13 |  | 0 |  |  | 110 | 0.0004126
3258 | 3258105 | Machinaries and Equipment | L.S | 0 | 0 | 14.87 |  | 95.13 |  | 0 |  |  | 110 | 0.0004126
|  | Sub Total |  |  |  | 192 |  | 1228 |  | 0 |  |  | 1420 | 0.0053263
|  | Total Revenue Component: A |  |  |  | 8065.41 |  | 18552.78 |  | 649.35 |  |  | 27267.54 | 0.10228
(B) Capital Component
Acquisition of Assets
4112 | 4112101 | Jeep | Nos | 100 | 7 | 73.5 |  | 626.5 |  | 0 |  |  | 700 | 0.0026257
4112 | 4112101 | Double Cabin Pickup/ Carryboy | Nos | 76.661 | 29 | 233.28 |  | 1989.89 |  |  |  |  | 2223.17 | 0.008339
4112 | 4112101 | Micro Bus | Nos | 76.515 | 2 | 16.07 |  | 136.96 |  |  |  |  | 153.03 | 0.00057401
4112 | 4112101 | Motor Cycle | Nos | 2.5521 | 24 | 6.48 |  | 54.77 |  |  |  |  | 61.25 | 0.00022974
4112 | 4112202 | Computers and Accessories | Nos | 1.994 | 163 | 34.12 |  | 290.91 |  | 0 |  |  | 325.03 | 0.0012192
4112 | 4112304 | Engineering and other Equipments | Nos/Set | 8.5387 | 660 | 591.73 |  | 5043.79 |  | 0 |  |  | 5635.52 | 0.021138
4112 | 4112314 | Furniture | L.S | 0 | 0 | 15.95 |  | 136.05 |  | 0 |  |  | 152 | 0.00057014
|  | Sub Total |  |  |  | 971.13 |  | 8278.87 |  | 0 |  |  | 9250 | 0.034696
4141 | 4141101 | Land Acquisition & Resettlement (Compensation for Land, structure & other assets including re-location, transitional training, vulnerable, documentation, monitoring, mitigation capacity measures & all other cost related to address ADB Safeguard issues) | Acre | 158.401 | 66.54 | 10540 |  | 0 |  | 0 |  |  | 10540 | 0.039535
|  | Sub Total |  |  |  | 10540 |  | 0 |  | 0 |  |  | 10540 | 0.039535
Construction of Works
|  | Stage-I | [10 empty] | 0
4111 | 4111304 | Roads | Km | 238.9632 | 298.387 | 8912.94 |  | 62390.56 |  | 0 |  |  | 71303.5 | 0.26745
4111 | 4111303 | Bridges | m | 13.9576 | 920 | 1605.13 |  | 11235.88 |  | 0 |  |  | 12841.01 | 0.048166
4111 | 4111307 | Drainage & Flood Control | Km | 334.3158 | 140.97 | 5891.06 |  | 41237.44 |  | 0 |  |  | 47128.5 | 0.17678
Others Structures
4111 | 4111317 | (a) Cyclone Shelters | Nos. | 464.9435 | 23 | 1336.71 |  | 9356.99 |  | 0 |  |  | 10693.7 | 0.040111
4111 | 4111317 | (b) Solid Waste Management | Nos. | 2125 | 4 | 1062.5 |  | 7437.5 |  | 0 |  |  | 8500 | 0.031883
4111 | 4111317 | (c) Green Space | Nos. | 750 | 2 | 187.5 |  | 1312.5 |  | 0 |  |  | 1500 | 0.0056264
4111 | 4111317 | (d) Nature-Base Solution | Nos. | 760 | 3 | 285 |  | 1995 |  | 0 |  |  | 2280 | 0.0085521
4111 | 4111317 | (e) Slum Improvement | Nos. | 79.5455 | 22 | 218.75 |  | 1531.25 |  | 0 |  |  | 1750 | 0.0065641
Stage-II
Others Structures
4111 | 4111317 | (a) Multipurpose Market | Nos. | 564.8571 | 21 | 1482.75 |  | 10379.25 |  | 0 |  |  | 11862 | 0.044494
4111 | 4111317 | (b) Bus Terminal | Nos. | 2125 | 4 | 1062.5 |  | 7437.5 |  | 0 |  |  | 8500 | 0.031883
4111 | 4111317 | (c) Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/ Bus Bay/Poltun etc. | Nos. | 458.2405 | 22 | 1260.16 |  | 8821.13 |  | 0 |  |  | 10081.29 | 0.037814
|  | Sub Total |  |  |  | 23305 |  | 163135 |  | 0 |  |  | 186440 | 0.69932
Block Allocation
4911 | 4911111 | Block Allocation (Commitment Charge) |  |  |  | 284 |  | 0 |  | 0 |  |  | 284 | 0.0010653
|  | Sub Total |  |  |  | 284 |  | 0 |  | 0 |  |  | 284 | 0.0010653
Loan & Advance
7215 | 7215205 | Interest during Implementation |  |  |  | 6563 |  | 0 |  | 0 |  |  | 6563 | 0.024617
|  | Sub Total |  |  |  | 6563 |  | 0 |  | 0 |  |  | 6563 | 0.024617
|  | Total Capital Component: B |  |  |  | 41663.13 |  | 171413.87 |  | 0 |  |  | 213077 | 0.79924
|  | Total (A+B) |  |  |  | 49728.54 |  | 189966.65 |  | 649.35 |  |  | 240344.54 | 0.90152
|  | (C) Physical Contingency |  |  |  | 1871.46 |  | 3142 |  | 0 |  |  | 5013.46 | 0.018805
|  | (D) Price Contingency |  |  |  | 0 |  | 21242 |  | 0 |  |  | 21242 | 0.079677
|  | Grand Total (A+B+C+D) |  |  |  | 51600 |  | 214350.65 |  | 649.35 |  |  | 266600 | 1
* DOSA, CONTASA, SAFE, Imprest etc.

## 9.0
9.0 Estimated Cost Summary
Name of the Project: Costal Towns Climate Resilience Project.
(Taka in Lac)
Economic Code | Economic Sub-Code | Economic Sub-Code wise Item Description | Unit | Quantity | Total Cost* | GOB (FE) | Project Aid |  |  |  | Own fund | Others | % of total Project cost
[7 empty] | RPA |  | DPA
[7 empty] | Through GOB | Special Account* | Through PD | Through DP
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
(A) Revenue Component
Pay of Officer:
3111 | 3111101 | Basic Pay (Officer) | PM | 1932 | 1236.48 | 1236.48 |  | 0 |  | 0 |  |  | 0.004638
|  | Sub Total |  |  | 1236.48 | 1236.48 |  | 0 |  | 0 |  |  | 0.004638
Pay of Empolyee:
3111 | 3111201 | Basic Pay (Employee) | PM | 504 | 204.01 | 204.01 |  | 0 |  | 0 |  |  | 0.00076523
|  | Sub Total |  |  | 204.01 | 204.01 |  | 0 |  | 0 |  |  | 0.00076523
Allowances:
3111 | 3111301 | Charge Allowance | PM | 420 | 23.94 | 23.94 |  | 0 |  | 0 |  |  | 8.9797e-05
3111 | 3111302 | Conveyance Allowance | PM | 504 | 1.52 | 1.52 |  | 0 |  | 0 |  |  | 5.7014e-06
3111 | 3111306 | Educational Allowance | PM | 2436 | 20.16 | 20.16 |  | 0 |  | 0 |  |  | 7.5619e-05
3111 | 3111310 | Housing Rent Allowances | PM | 2436 | 854.34 | 854.34 |  | 0 |  | 0 |  |  | 0.0032046
3111 | 3111311 | Medical Allowance | PM | 2436 | 36.54 | 36.54 |  | 0 |  | 0 |  |  | 0.00013706
3111 | 3111312 | Mobile/Cell Phone Allowance | PM | 420 | 6.72 | 6.72 |  | 0 |  | 0 |  |  | 2.5206e-05
3111 | 3111314 | Tiffin Allowance | PM | 504 | 1.52 | 1.52 |  | 0 |  | 0 |  |  | 5.7014e-06
3111 | 3111325 | Festival Allowance | Nos. | 435 | 283.6 | 283.6 |  | 0 |  | 0 |  |  | 0.0010638
3111 | 3111328 | Rest & Recreation Allowance | Nos. | 87 | 52.2 | 52.2 |  | 0 |  | 0 |  |  | 0.0001958
3111 | 3111335 | Bangla New Year Allowance | Nos. | 232 | 34.8 | 34.8 |  | 0 |  | 0 |  |  | 0.00013053
3111 | 3111338 | Other Allowance | L.S | 232 | 276.16 | 276.16 |  | 0 |  | 0 |  |  | 0.0010359
|  | Sub Total |  |  | 1591.5 | 1591.5 |  | 0 |  | 0 |  |  | 0.0059696
Supplies and Services:
3211 | 3211111 | Seminar & Conference Expenses | Nos. | 30 | 230 | 24.15 |  | 205.85 |  | 0 |  |  | 0.00086272 | 230 | 24.15 | 205.85
3211 | 3211113 | Electricity | Month | 84 | 240 | 25.2 |  | 214.8 |  | 0 |  |  | 0.00090023 | 240 | 25.2 | 214.8
3211 | 3211119 | Postage | Month | 84 | 10 | 1 |  | 9 |  | 0 |  |  | 3.7509e-05 | 10 | 1.05 | 8.95
3211 | 3211120 | Telephone | Month | 84 | 65 | 6.82 |  | 58.18 |  | 0 |  |  | 0.00024381 | 65 | 6.825 | 58.175
3211 | 3211125 | Advertising Expenses | Nos. | 678 | 285 | 29.92 |  | 255.08 |  | 0 |  |  | 0.001069 | 285 | 29.925 | 255.075
3211 | 3211126 | Audio -VDO/Film Production | Nos. | 23 | 50 | 5.25 |  | 44.75 |  | 0 |  |  | 0.00018755 | 65 | 6.825 | 58.175
3211 | 3211128 | Publications | L.S | 0 | 85 | 8.9 |  | 76.1 |  | 0 |  |  | 0.00031883 | 85 | 8.925 | 76.075
3211 | 3211131 | Out sourcing | PM | 8820 | 3150 | 330.75 |  | 2819.25 |  | 0 |  |  | 0.011815 | 3150 | 330.75 | 2819.25
3221 | 3221104 | Registration Fee | L.S | 0 | 324.9 | 34.1 |  | 290.8 |  | 0 |  |  | 0.0012187 | 325 | 34.125 | 290.875
3231 | 3231201 | DomesticTraining | Nos. | 50 | 375 | 39.35 |  | 335.65 |  | 0 |  |  | 0.0014066 | 375 | 39.375 | 335.625
3231 | 3231101 | ForeignTraining | Nos. | 3 | 350 | 36.72 |  | 313.28 |  | 0 |  |  | 0.0013128
3241 | 3241101 | Domestic Travel Expenses | L.S | 0 | 364.75 | 38.34 |  | 326.41 |  | 0 |  |  | 0.0013682 | 465 | 48.825 | 416.175
3241 | 3241102 | Domestic Trasfer Expenses | L.S | 0 | 50 | 5.25 |  | 44.75 |  | 0 |  |  | 0.00018755 | 75 | 7.875 | 67.125
3243 | 3243101 | Petrol, Oil and Lubricants | L.S | 0 | 850 | 89.25 |  | 760.75 |  | 0 |  |  | 0.0031883 | 850 | 89.25 | 760.75
3243 | 3243102 | Gas and Fuel | L.S | 0 | 540 | 56.7 |  | 483.3 |  | 0 |  |  | 0.0020255 | 540 | 56.7 | 483.3
3255 | 3255101 | Computer Consumables | L.S | 0 | 250 | 26.25 |  | 223.75 |  | 0 |  |  | 0.00093773 | 250 | 26.25 | 223.75
3255 | 3255104 | Stamps & Seals | L.S | 0 | 21 | 2.2 |  | 18.8 |  | 0 |  |  | 7.877e-05 | 21 | 2.205 | 18.795
3255 | 3255105 | Others Stationery | L.S | 0 | 208 | 21.85 |  | 186.15 |  | 0 |  |  | 0.0007802 | 208 | 21.84 | 186.16
3257 | 3257101 | Consultancy | PM | 4544 | 14341 | 3952 |  | 9739.65 |  | 649.35 |  |  | 0.053792
3257 | 3257104 | Survey | Nos. | 110 | 855.9 | 89.7 |  | 766.2 |  | 0 |  |  | 0.0032104 | 855 | 89.775 | 765.225
3257 | 3257206 | Honorarium / Remuneration | Nos. | 510 | 170 | 17.72 |  | 152.28 |  | 0 |  |  | 0.00063766 | 170 | 17.85 | 152.15
|  | Sub Total |  |  | 22815.55 | 4841.42 |  | 17324.78 |  | 649.35 |  |  | 0.08558
Repair, Maintenance and Rehabilitation
3258 | 3258101 | Motor Vehicle | L.S | 0 | 1062 | 143.6 |  | 918.4 |  | 0 |  |  | 0.0039835
3258 | 3258102 | Furniture | L.S | 0 | 138 | 18.66 |  | 119.34 |  | 0 |  |  | 0.00051763
3258 | 3258103 | Computer | L.S | 0 | 110 | 14.87 |  | 95.13 |  | 0 |  |  | 0.0004126
3258 | 3258105 | Machinaries and Equipment | L.S | 0 | 110 | 14.87 |  | 95.13 |  | 0 |  |  | 0.0004126
|  | Sub Total |  |  | 1420 | 192 |  | 1228 |  | 0 |  |  | 0.0053263
|  | Total Revenue Component: A |  |  | 27267.54 | 8065.41 |  | 18552.78 |  | 649.35 |  |  | 0.10228
(B) Capital Component
Acquisition of Assets
4112 | 4112101 | Jeep | Nos | 7 | 700 | 73.5 |  | 626.5 |  | 0 |  |  | 0.0026257 | 700 | 73.5 | 626.5
4112 | 4112101 | Double Cabin Pickup/ Carryboy | Nos | 29 | 2223.17 | 233.28 |  | 1989.89 | [5 empty] | 2222.85 | 233.3992 | 1989.4507
4112 | 4112101 | Micro Bus | Nos | 2 | 153.03 | 16.07 |  | 136.96 | [5 empty] | 153.03 | 16.0681 | 136.9618
4112 | 4112101 | Motor Cycle | Nos | 24 | 61.25 | 6.48 |  | 54.77 | [5 empty] | 61.2 | 6.426 | 54.774
4112 | 4112202 | Computers and Accessories | Nos | 163 | 325.03 | 34.12 |  | 290.91 |  | 0 |  |  | 0.0012192 | 3137.08 | 329.3934 | 2807.6866
4112 | 4112304 | Engineering and other Equipments | Nos/Set | 660 | 5635.52 | 591.73 |  | 5043.79 |  | 0 |  |  | 0.021138 | 5585.52 | 586.4796 | 4999.0404
4112 | 4112314 | Furniture | L.S | 0 | 152 | 15.95 |  | 136.05 |  | 0 |  |  | 0.00057014
|  | Sub Total |  |  | 9250 | 971.13 |  | 8278.87 |  | 0 |  |  | 0.025553
4141 | 4141101 | Land Acquisition & Resettlement (Compensation for Land, structure & other assets including re-location, transitional training, vulnerable, documentation, monitoring, mitigation capacity measures & all other cost related to address ADB Safeguard issues) | Acre | 66.54 | 10540 | 10540 |  | 0 |  | 0 |  |  | 0.039535
|  | Sub Total |  |  | 10540 | 10540 |  | 0 |  | 0 |  |  | 0.039535
Construction of Works
Stage-I
4111 | 4111304 | Roads | Km | 298.387 | 71303.5 | 8912.94 |  | 62390.56 |  | 0 |  |  | 0.26745
4111 | 4111303 | Bridges | m | 920 | 12841.01 | 1605.13 |  | 11235.88 |  | 0 |  |  | 0.048166
4111 | 4111307 | Drainage & Flood Control | Km | 140.97 | 47128.5 | 5891.06 |  | 41237.44 |  | 0 |  |  | 0.17678
|  | Others Structures | [10 empty] | 0
4111 | 4111317 | (a) Cyclone Shelters | Nos. | 23 | 10693.7 | 1336.71 |  | 9356.99 |  | 0 |  |  | 0.040111
4111 | 4111317 | (b) Solid Waste Management | Nos. | 4 | 8500 | 1062.5 |  | 7437.5 |  | 0 |  |  | 0.031883
4111 | 4111317 | (c) Green Space | Nos. | 2 | 1500 | 187.5 |  | 1312.5 |  | 0 |  |  | 0.0056264
4111 | 4111317 | (d) Nature-Base Solution | Nos. | 3 | 2280 | 285 |  | 1995 |  | 0 |  |  | 0.0085521
4111 | 4111317 | (e) Slum Improvement | Nos. | 22 | 1750 | 218.75 |  | 1531.25 |  | 0 |  |  | 0.0065641
|  | Stage-II | [10 empty] | 0
Others Structures
4111 | 4111317 | (a) Multipurpose Market | Nos. | 21 | 11862 | 1482.75 |  | 10379.25 |  | 0 |  |  | 0.044494
4111 | 4111317 | (b) Bus Terminal | Nos. | 4 | 8500 | 1062.5 |  | 7437.5 |  | 0 |  |  | 0.031883
4111 | 4111317 | (c) Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/ Bus Bay/Poltun etc. | Nos. | 22 | 10081.29 | 1260.16 |  | 8821.13 |  | 0 |  |  | 0.037814
|  | Sub Total |  |  | 186440 | 23305 |  | 163135 |  | 0 |  |  | 0.69932
Block Allocation
4911 | 4911111 | Block Allocation (Commitment Charge) |  |  | 284 | 284 |  | 0 |  | 0 |  |  | 0.0010653
|  | Sub Total |  |  | 284 | 284 |  | 0 |  | 0 |  |  | 0.0010653
Loan & Advance
7215 | 7215205 | Interest during Implementation |  |  | 6563 | 6563 |  | 0 |  | 0 |  |  | 0.024617
|  | Sub Total |  |  | 6563 | 6563 |  | 0 |  | 0 |  |  | 0.024617
|  | Total Capital Component: B |  |  | 213077 | 41663.13 |  | 171413.87 |  | 0 |  |  | 0.7901
|  | Total (A+B) |  |  | 240344.54 | 49728.54 |  | 189966.65 |  | 649.35 |  |  | 0.89237
|  | (C) Physical Contingency |  |  | 5013.46 | 1871.46 |  | 3142 |  | 0 |  |  | 0.018805
|  | (D) Price Contingency |  |  | 21242 | 0 |  | 21242 |  | 0 |  |  | 0.079677
|  | Grand Total (A+B+C+D) |  |  | 266600 | 51600 |  | 214350.65 |  | 649.35 |  |  | 0.99086
* Column 6=(7+8+9+10+11+12+13)
** DOSA, CONTASA, SAFE, Imprest, etc.